## BL-Activities
Activity ID | Activity Name | Original Duration | Start | Finish | Early Start | Early Finish | Late Start | Late Finish | Total Float | Activity Type | L01 | L02 | L03 | L04
A1010 | Mobilization and Site Office Installation | 30 | 2018-01-01 | 2018-01-30 | 2018-01-01 | 2018-01-30 | 2018-01-01 | 2018-01-30 | 0 | Task Dependent | L01-01 | (New)-1 | (New)-1 | (New)-1
KEY-16 | Project Start Date | 0 | 2018-01-01 |  | 2018-01-01 |  | 2018-01-01 |  | 0 | Start Milestone | L01-01 | (New) | (New) | (New)
1-SUB-100 | Concrete | 7 | 2018-01-11 | 2018-01-17 | 2018-01-11 | 2018-01-17 | 2018-01-28 | 2018-02-03 | 17 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
2-MS1000 | Concrete | 7 | 2018-01-18 | 2018-01-24 | 2018-01-18 | 2018-01-24 | 2018-02-04 | 2018-02-10 | 17 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1000 | Concrete | 7 | 2018-01-25 | 2018-01-31 | 2018-01-25 | 2018-01-31 | 2018-02-11 | 2018-02-17 | 17 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
A1030 | Excavation Works | 25 | 2018-01-31 | 2018-02-24 | 2018-01-31 | 2018-02-24 | 2018-01-31 | 2018-02-24 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-8
KEY-26 | Start Construction | 0 | 2018-01-31 |  | 2018-01-31 |  | 2018-01-31 |  | 0 | Start Milestone | L01-01 | (New) | (New) | (New)
4-MD1000 | Concrete | 7 | 2018-02-01 | 2018-02-07 | 2018-02-01 | 2018-02-07 | 2018-02-18 | 2018-02-24 | 17 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
1-SUB-110 | Block | 7 | 2018-02-20 | 2018-02-26 | 2018-02-20 | 2018-02-26 | 2018-05-03 | 2018-05-09 | 72 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-150 | AC Machine | 7 | 2018-02-20 | 2018-02-26 | 2018-02-20 | 2018-02-26 | 2018-05-13 | 2018-05-19 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-160 | Electrical | 7 | 2018-02-20 | 2018-02-26 | 2018-02-20 | 2018-02-26 | 2018-05-13 | 2018-05-19 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-170 | Plumbing | 7 | 2018-02-20 | 2018-02-26 | 2018-02-20 | 2018-02-26 | 2018-05-13 | 2018-05-19 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-200 | Fire Fighting | 7 | 2018-02-20 | 2018-02-26 | 2018-02-20 | 2018-02-26 | 2018-05-13 | 2018-05-19 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
A1050 | Foundation Works | 45 | 2018-02-25 | 2018-04-10 | 2018-02-25 | 2018-04-10 | 2018-02-25 | 2018-04-10 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-8
2-MS1010 | Block | 7 | 2018-02-27 | 2018-03-05 | 2018-02-27 | 2018-03-05 | 2018-05-10 | 2018-05-16 | 72 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1050 | AC Machine | 7 | 2018-02-27 | 2018-03-05 | 2018-02-27 | 2018-03-05 | 2018-05-20 | 2018-05-26 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1060 | Electrical | 7 | 2018-02-27 | 2018-03-05 | 2018-02-27 | 2018-03-05 | 2018-05-20 | 2018-05-26 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1070 | Plumbing | 7 | 2018-02-27 | 2018-03-05 | 2018-02-27 | 2018-03-05 | 2018-05-20 | 2018-05-26 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1100 | Fire Fighting | 7 | 2018-02-27 | 2018-03-05 | 2018-02-27 | 2018-03-05 | 2018-05-20 | 2018-05-26 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
1-SDS100 | Structural Drawings | 14 | 2018-03-02 | 2018-03-15 | 2018-03-02 | 2018-03-15 | 2018-03-14 | 2018-03-27 | 12 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
3-MA1010 | Block | 7 | 2018-03-06 | 2018-03-12 | 2018-03-06 | 2018-03-12 | 2018-05-17 | 2018-05-23 | 72 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1050 | AC Machine | 7 | 2018-03-06 | 2018-03-12 | 2018-03-06 | 2018-03-12 | 2018-05-27 | 2018-06-02 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1060 | Electrical | 7 | 2018-03-06 | 2018-03-12 | 2018-03-06 | 2018-03-12 | 2018-05-27 | 2018-06-02 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1070 | Plumbing | 7 | 2018-03-06 | 2018-03-12 | 2018-03-06 | 2018-03-12 | 2018-05-27 | 2018-06-02 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1100 | Fire Fighting | 7 | 2018-03-06 | 2018-03-12 | 2018-03-06 | 2018-03-12 | 2018-05-27 | 2018-06-02 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
4-MD1010 | Block | 7 | 2018-03-13 | 2018-03-19 | 2018-03-13 | 2018-03-19 | 2018-05-24 | 2018-05-30 | 72 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1050 | AC Machine | 60 | 2018-03-13 | 2018-05-11 | 2018-03-13 | 2018-05-11 | 2018-06-03 | 2018-08-01 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1060 | Electrical | 60 | 2018-03-13 | 2018-05-11 | 2018-03-13 | 2018-05-11 | 2018-06-03 | 2018-08-01 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1070 | Plumbing | 60 | 2018-03-13 | 2018-05-11 | 2018-03-13 | 2018-05-11 | 2018-06-03 | 2018-08-01 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1100 | Fire Fighting | 60 | 2018-03-13 | 2018-05-11 | 2018-03-13 | 2018-05-11 | 2018-06-03 | 2018-08-01 | 82 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
2-SDA1000 | Structural Drawings | 14 | 2018-03-16 | 2018-03-29 | 2018-03-16 | 2018-03-29 | 2018-03-28 | 2018-04-10 | 12 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
A1210 | Ground Floor Slab | 20 | 2018-04-11 | 2018-04-30 | 2018-04-11 | 2018-04-30 | 2018-04-11 | 2018-04-30 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-9
1-SUB-120 | Ceramic | 7 | 2018-04-11 | 2018-04-17 | 2018-04-11 | 2018-04-17 | 2018-04-25 | 2018-05-01 | 14 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-130 | Doors and window | 7 | 2018-04-11 | 2018-04-17 | 2018-04-11 | 2018-04-17 | 2018-05-07 | 2018-05-13 | 26 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SDS110 | Finishes Drawings | 14 | 2018-04-11 | 2018-04-24 | 2018-04-11 | 2018-04-24 | 2018-05-03 | 2018-05-16 | 22 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
2-MS1020 | Ceramic | 7 | 2018-04-18 | 2018-04-24 | 2018-04-18 | 2018-04-24 | 2018-05-02 | 2018-05-08 | 14 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1030 | Doors and window | 7 | 2018-04-18 | 2018-04-24 | 2018-04-18 | 2018-04-24 | 2018-05-14 | 2018-05-20 | 26 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1020 | Ceramic | 7 | 2018-04-25 | 2018-05-01 | 2018-04-25 | 2018-05-01 | 2018-05-09 | 2018-05-15 | 14 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1030 | Doors and window | 7 | 2018-04-25 | 2018-05-01 | 2018-04-25 | 2018-05-01 | 2018-05-21 | 2018-05-27 | 26 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
2-SDA1010 | Finishes Drawings | 14 | 2018-04-25 | 2018-05-08 | 2018-04-25 | 2018-05-08 | 2018-05-17 | 2018-05-30 | 22 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
A1220 | Ground Floor Columns | 15 | 2018-05-01 | 2018-05-15 | 2018-05-01 | 2018-05-15 | 2018-05-01 | 2018-05-15 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-9
1-SUB-140 | Wood Works | 7 | 2018-05-01 | 2018-05-07 | 2018-05-01 | 2018-05-07 | 2018-06-21 | 2018-06-27 | 51 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-180 | Mirrors & Bath Accessories | 7 | 2018-05-01 | 2018-05-07 | 2018-05-01 | 2018-05-07 | 2018-11-29 | 2018-12-05 | 212 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SDS120 | Mechanical Drawings | 14 | 2018-05-01 | 2018-05-14 | 2018-05-01 | 2018-05-14 | 2018-07-05 | 2018-07-18 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
1-SDS130 | Electrical Drawings | 14 | 2018-05-01 | 2018-05-14 | 2018-05-01 | 2018-05-14 | 2018-07-05 | 2018-07-18 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
1-SDS140 | Fire Fighting Drawings | 14 | 2018-05-01 | 2018-05-14 | 2018-05-01 | 2018-05-14 | 2018-07-05 | 2018-07-18 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
1-SDS150 | Plumbing Drawings | 14 | 2018-05-01 | 2018-05-14 | 2018-05-01 | 2018-05-14 | 2018-07-05 | 2018-07-18 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
4-MD1020 | Ceramic | 60 | 2018-05-02 | 2018-06-30 | 2018-05-02 | 2018-06-30 | 2018-05-16 | 2018-07-14 | 14 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1030 | Doors and window | 60 | 2018-05-02 | 2018-06-30 | 2018-05-02 | 2018-06-30 | 2018-05-28 | 2018-07-26 | 26 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
2-MS1040 | Wood Works | 7 | 2018-05-08 | 2018-05-14 | 2018-05-08 | 2018-05-14 | 2018-06-28 | 2018-07-04 | 51 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1080 | Mirrors & Bath Accessories | 7 | 2018-05-08 | 2018-05-14 | 2018-05-08 | 2018-05-14 | 2018-12-06 | 2018-12-12 | 212 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1040 | Wood Works | 7 | 2018-05-15 | 2018-05-21 | 2018-05-15 | 2018-05-21 | 2018-07-05 | 2018-07-11 | 51 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1080 | Mirrors & Bath Accessories | 7 | 2018-05-15 | 2018-05-21 | 2018-05-15 | 2018-05-21 | 2018-12-13 | 2018-12-19 | 212 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
2-SDA1020 | Mechanical Drawings | 14 | 2018-05-15 | 2018-05-28 | 2018-05-15 | 2018-05-28 | 2018-07-19 | 2018-08-01 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1030 | Electrical Drawings | 14 | 2018-05-15 | 2018-05-28 | 2018-05-15 | 2018-05-28 | 2018-07-19 | 2018-08-01 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1040 | Fire Fighting Drawings | 14 | 2018-05-15 | 2018-05-28 | 2018-05-15 | 2018-05-28 | 2018-07-19 | 2018-08-01 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1050 | Plumbing Drawings | 14 | 2018-05-15 | 2018-05-28 | 2018-05-15 | 2018-05-28 | 2018-07-19 | 2018-08-01 | 65 | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
A1230 | Roof Slab | 15 | 2018-05-16 | 2018-05-30 | 2018-05-16 | 2018-05-30 | 2018-05-16 | 2018-05-30 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-10
4-MD1040 | Wood Works | 60 | 2018-05-22 | 2018-07-20 | 2018-05-22 | 2018-07-20 | 2018-07-12 | 2018-09-09 | 51 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1080 | Mirrors & Bath Accessories | 60 | 2018-05-22 | 2018-07-20 | 2018-05-22 | 2018-07-20 | 2018-12-20 | 2019-02-17 | 212 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
A1240 | Parapet | 12 | 2018-05-31 | 2018-06-11 | 2018-05-31 | 2018-06-11 | 2018-10-14 | 2018-10-25 | 136 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-10
A1250 | Block Works | 20 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-06-19 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1410 | Roof Waterproofing woks | 5 | 2018-05-31 | 2018-06-04 | 2018-05-31 | 2018-06-04 | 2019-03-05 | 2019-03-09 | 278 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | 10 | 2018-06-20 | 2018-06-29 | 2018-06-20 | 2018-06-29 | 2018-06-20 | 2018-06-29 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
A1260 | Plaster | 15 | 2018-06-30 | 2018-07-14 | 2018-06-30 | 2018-07-14 | 2018-06-30 | 2018-07-14 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1270 | Ceramic | 12 | 2018-07-15 | 2018-07-26 | 2018-07-15 | 2018-07-26 | 2018-07-15 | 2018-07-26 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1310 | Plaster | 10 | 2018-07-15 | 2018-07-24 | 2018-07-15 | 2018-07-24 | 2018-10-26 | 2018-11-04 | 103 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1320 | Painting | 15 | 2018-07-25 | 2018-08-08 | 2018-07-25 | 2018-08-08 | 2018-11-05 | 2018-11-19 | 103 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1400 | Balcony Handrails | 5 | 2018-07-25 | 2018-07-29 | 2018-07-25 | 2018-07-29 | 2019-03-05 | 2019-03-09 | 223 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | 30 | 2018-07-27 | 2018-08-25 | 2018-07-27 | 2018-08-25 | 2018-08-02 | 2018-08-31 | 6 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
A1300 | Doors and windows Works | 15 | 2018-07-27 | 2018-08-10 | 2018-07-27 | 2018-08-10 | 2018-07-27 | 2018-08-10 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
1-SUB-190 | Landscaping | 7 | 2018-08-09 | 2018-08-15 | 2018-08-09 | 2018-08-15 | 2018-11-09 | 2018-11-15 | 92 | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
A1340 | Epoxy Coating-Services Area | 30 | 2018-08-11 | 2018-09-09 | 2018-08-11 | 2018-09-09 | 2018-08-11 | 2018-09-09 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
2-MS1090 | Landscaping | 7 | 2018-08-16 | 2018-08-22 | 2018-08-16 | 2018-08-22 | 2018-11-16 | 2018-11-22 | 92 | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1090 | Landscaping | 7 | 2018-08-23 | 2018-08-29 | 2018-08-23 | 2018-08-29 | 2018-11-23 | 2018-11-29 | 92 | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
A1280 | Ceiling Works | 30 | 2018-08-26 | 2018-09-24 | 2018-08-26 | 2018-09-24 | 2018-09-01 | 2018-09-30 | 6 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
4-MD1090 | Landscaping | 60 | 2018-08-30 | 2018-10-28 | 2018-08-30 | 2018-10-28 | 2018-11-30 | 2019-01-28 | 92 | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
A1350 | Kitchen Cabinets | 12 | 2018-09-10 | 2018-09-21 | 2018-09-10 | 2018-09-21 | 2018-09-10 | 2018-09-21 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1360 | Vanity Counter | 4 | 2018-09-22 | 2018-09-25 | 2018-09-22 | 2018-09-25 | 2018-09-22 | 2018-09-25 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1370 | Wooden Doors | 5 | 2018-09-26 | 2018-09-30 | 2018-09-26 | 2018-09-30 | 2018-09-26 | 2018-09-30 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1290 | Painting - 1st Coat | 10 | 2018-10-01 | 2018-10-10 | 2018-10-01 | 2018-10-10 | 2018-10-01 | 2018-10-10 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | 40 | 2018-10-11 | 2018-11-19 | 2018-10-11 | 2018-11-19 | 2018-10-11 | 2018-11-19 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
A1380 | Wardrobes | 50 | 2018-10-31 | 2018-12-19 | 2018-10-31 | 2018-12-19 | 2018-12-27 | 2019-02-14 | 57 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
KEY-46 | Completion of Construction For Villa Building | 0 |  | 2018-11-19 |  | 2018-11-19 |  | 2018-11-19 | 0 | Finish Milestone | L01-01 | (New) | (New) | (New)
E1070 | Fence Works | 50 | 2018-11-20 | 2019-01-08 | 2018-11-20 | 2019-01-08 | 2018-11-20 | 2019-01-08 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
KEY-36 | Start Construction For External Works | 0 | 2018-11-20 |  | 2018-11-20 |  | 2018-11-20 |  | 0 | Start Milestone | L01-01 | (New) | (New) | (New)
A1330 | Painting Final Coat | 8 | 2018-12-15 | 2018-12-22 | 2018-12-15 | 2018-12-22 | 2019-02-10 | 2019-02-17 | 57 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1390 | Mirrors & Bath Accessories | 20 | 2018-12-23 | 2019-01-11 | 2018-12-23 | 2019-01-11 | 2019-02-18 | 2019-03-09 | 57 | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
HOV110 | Submission of As Built Drawings | 10 | 2018-12-30 | 2019-01-08 | 2018-12-30 | 2019-01-08 | 2019-02-28 | 2019-03-09 | 60 | Task Dependent | L01-01 | (New)-5 | (New)-10 | (New)-15
E1071 | External Tiling Works | 25 | 2019-01-09 | 2019-02-02 | 2019-01-09 | 2019-02-02 | 2019-02-13 | 2019-03-09 | 35 | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
E1080 | Installation of Wheel Stopper & Corner Gaurd | 60 | 2019-01-09 | 2019-03-09 | 2019-01-09 | 2019-03-09 | 2019-01-09 | 2019-03-09 | 0 | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
E1081 | Green Area Works | 40 | 2019-01-17 | 2019-02-25 | 2019-01-17 | 2019-02-25 | 2019-01-29 | 2019-03-09 | 12 | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
KEY-56 | Completion of Construction For External Works | 0 |  | 2019-02-25 |  | 2019-02-25 |  | 2019-03-09 | 12 | Finish Milestone | L01-01 | (New) | (New) | (New)
A1080 | Project Handing Over and Authority approvals | 20 | 2019-03-10 | 2019-03-29 | 2019-03-10 | 2019-03-29 | 2019-03-10 | 2019-03-29 | 0 | Task Dependent | L01-01 | (New)-5 | (New)-10 | (New)-15
KEY-6 | Project Finish Date | 0 |  | 2019-03-29 |  | 2019-03-29 |  | 2019-03-29 | 0 | Finish Milestone | L01-01 | (New) | (New) | (New)

## BL-Res
Activity ID | Activity Name | Resource ID | Resource Name | Budgeted Units | Budgeted Cost | Spreadsheet Field | 01-Jan-18 | 02-Jan-18 | 03-Jan-18 | 04-Jan-18 | 05-Jan-18 | 06-Jan-18 | 07-Jan-18 | 08-Jan-18 | 09-Jan-18 | 10-Jan-18 | 11-Jan-18 | 12-Jan-18 | 13-Jan-18 | 14-Jan-18 | 15-Jan-18 | 16-Jan-18 | 17-Jan-18 | 18-Jan-18 | 19-Jan-18 | 20-Jan-18 | 21-Jan-18 | 22-Jan-18 | 23-Jan-18 | 24-Jan-18 | 25-Jan-18 | 26-Jan-18 | 27-Jan-18 | 28-Jan-18 | 29-Jan-18 | 30-Jan-18 | 31-Jan-18 | 01-Feb-18 | 02-Feb-18 | 03-Feb-18 | 04-Feb-18 | 05-Feb-18 | 06-Feb-18 | 07-Feb-18 | 08-Feb-18 | 09-Feb-18 | 10-Feb-18 | 11-Feb-18 | 12-Feb-18 | 13-Feb-18 | 14-Feb-18 | 15-Feb-18 | 16-Feb-18 | 17-Feb-18 | 18-Feb-18 | 19-Feb-18 | 20-Feb-18 | 21-Feb-18 | 22-Feb-18 | 23-Feb-18 | 24-Feb-18 | 25-Feb-18 | 26-Feb-18 | 27-Feb-18 | 28-Feb-18 | 01-Mar-18 | 02-Mar-18 | 03-Mar-18 | 04-Mar-18 | 05-Mar-18 | 06-Mar-18 | 07-Mar-18 | 08-Mar-18 | 09-Mar-18 | 10-Mar-18 | 11-Mar-18 | 12-Mar-18 | 13-Mar-18 | 14-Mar-18 | 15-Mar-18 | 16-Mar-18 | 17-Mar-18 | 18-Mar-18 | 19-Mar-18 | 20-Mar-18 | 21-Mar-18 | 22-Mar-18 | 23-Mar-18 | 24-Mar-18 | 25-Mar-18 | 26-Mar-18 | 27-Mar-18 | 28-Mar-18 | 29-Mar-18 | 30-Mar-18 | 31-Mar-18 | 01-Apr-18 | 02-Apr-18 | 03-Apr-18 | 04-Apr-18 | 05-Apr-18 | 06-Apr-18 | 07-Apr-18 | 08-Apr-18 | 09-Apr-18 | 10-Apr-18 | 11-Apr-18 | 12-Apr-18 | 13-Apr-18 | 14-Apr-18 | 15-Apr-18 | 16-Apr-18 | 17-Apr-18 | 18-Apr-18 | 19-Apr-18 | 20-Apr-18 | 21-Apr-18 | 22-Apr-18 | 23-Apr-18 | 24-Apr-18 | 25-Apr-18 | 26-Apr-18 | 27-Apr-18 | 28-Apr-18 | 29-Apr-18 | 30-Apr-18 | 01-May-18 | 02-May-18 | 03-May-18 | 04-May-18 | 05-May-18 | 06-May-18 | 07-May-18 | 08-May-18 | 09-May-18 | 10-May-18 | 11-May-18 | 12-May-18 | 13-May-18 | 14-May-18 | 15-May-18 | 16-May-18 | 17-May-18 | 18-May-18 | 19-May-18 | 20-May-18 | 21-May-18 | 22-May-18 | 23-May-18 | 24-May-18 | 25-May-18 | 26-May-18 | 27-May-18 | 28-May-18 | 29-May-18 | 30-May-18 | 31-May-18 | 01-Jun-18 | 02-Jun-18 | 03-Jun-18 | 04-Jun-18 | 05-Jun-18 | 06-Jun-18 | 07-Jun-18 | 08-Jun-18 | 09-Jun-18 | 10-Jun-18 | 11-Jun-18 | 12-Jun-18 | 13-Jun-18 | 14-Jun-18 | 15-Jun-18 | 16-Jun-18 | 17-Jun-18 | 18-Jun-18 | 19-Jun-18 | 20-Jun-18 | 21-Jun-18 | 22-Jun-18 | 23-Jun-18 | 24-Jun-18 | 25-Jun-18 | 26-Jun-18 | 27-Jun-18 | 28-Jun-18 | 29-Jun-18 | 30-Jun-18 | 01-Jul-18 | 02-Jul-18 | 03-Jul-18 | 04-Jul-18 | 05-Jul-18 | 06-Jul-18 | 07-Jul-18 | 08-Jul-18 | 09-Jul-18 | 10-Jul-18 | 11-Jul-18 | 12-Jul-18 | 13-Jul-18 | 14-Jul-18 | 15-Jul-18 | 16-Jul-18 | 17-Jul-18 | 18-Jul-18 | 19-Jul-18 | 20-Jul-18 | 21-Jul-18 | 22-Jul-18 | 23-Jul-18 | 24-Jul-18 | 25-Jul-18 | 26-Jul-18 | 27-Jul-18 | 28-Jul-18 | 29-Jul-18 | 30-Jul-18 | 31-Jul-18 | 01-Aug-18 | 02-Aug-18 | 03-Aug-18 | 04-Aug-18 | 05-Aug-18 | 06-Aug-18 | 07-Aug-18 | 08-Aug-18 | 09-Aug-18 | 10-Aug-18 | 11-Aug-18 | 12-Aug-18 | 13-Aug-18 | 14-Aug-18 | 15-Aug-18 | 16-Aug-18 | 17-Aug-18 | 18-Aug-18 | 19-Aug-18 | 20-Aug-18 | 21-Aug-18 | 22-Aug-18 | 23-Aug-18 | 24-Aug-18 | 25-Aug-18 | 26-Aug-18 | 27-Aug-18 | 28-Aug-18 | 29-Aug-18 | 30-Aug-18 | 31-Aug-18 | 01-Sep-18 | 02-Sep-18 | 03-Sep-18 | 04-Sep-18 | 05-Sep-18 | 06-Sep-18 | 07-Sep-18 | 08-Sep-18 | 09-Sep-18 | 10-Sep-18 | 11-Sep-18 | 12-Sep-18 | 13-Sep-18 | 14-Sep-18 | 15-Sep-18 | 16-Sep-18 | 17-Sep-18 | 18-Sep-18 | 19-Sep-18 | 20-Sep-18 | 21-Sep-18 | 22-Sep-18 | 23-Sep-18 | 24-Sep-18 | 25-Sep-18 | 26-Sep-18 | 27-Sep-18 | 28-Sep-18 | 29-Sep-18 | 30-Sep-18 | 01-Oct-18 | 02-Oct-18 | 03-Oct-18 | 04-Oct-18 | 05-Oct-18 | 06-Oct-18 | 07-Oct-18 | 08-Oct-18 | 09-Oct-18 | 10-Oct-18 | 11-Oct-18 | 12-Oct-18 | 13-Oct-18 | 14-Oct-18 | 15-Oct-18 | 16-Oct-18 | 17-Oct-18 | 18-Oct-18 | 19-Oct-18 | 20-Oct-18 | 21-Oct-18 | 22-Oct-18 | 23-Oct-18 | 24-Oct-18 | 25-Oct-18 | 26-Oct-18 | 27-Oct-18 | 28-Oct-18 | 29-Oct-18 | 30-Oct-18 | 31-Oct-18 | 01-Nov-18 | 02-Nov-18 | 03-Nov-18 | 04-Nov-18 | 05-Nov-18 | 06-Nov-18 | 07-Nov-18 | 08-Nov-18 | 09-Nov-18 | 10-Nov-18 | 11-Nov-18 | 12-Nov-18 | 13-Nov-18 | 14-Nov-18 | 15-Nov-18 | 16-Nov-18 | 17-Nov-18 | 18-Nov-18 | 19-Nov-18 | 20-Nov-18 | 21-Nov-18 | 22-Nov-18 | 23-Nov-18 | 24-Nov-18 | 25-Nov-18 | 26-Nov-18 | 27-Nov-18 | 28-Nov-18 | 29-Nov-18 | 30-Nov-18 | 01-Dec-18 | 02-Dec-18 | 03-Dec-18 | 04-Dec-18 | 05-Dec-18 | 06-Dec-18 | 07-Dec-18 | 08-Dec-18 | 09-Dec-18 | 10-Dec-18 | 11-Dec-18 | 12-Dec-18 | 13-Dec-18 | 14-Dec-18 | 15-Dec-18 | 16-Dec-18 | 17-Dec-18 | 18-Dec-18 | 19-Dec-18 | 20-Dec-18 | 21-Dec-18 | 22-Dec-18 | 23-Dec-18 | 24-Dec-18 | 25-Dec-18 | 26-Dec-18 | 27-Dec-18 | 28-Dec-18 | 29-Dec-18 | 30-Dec-18 | 31-Dec-18 | 01-Jan-19 | 02-Jan-19 | 03-Jan-19 | 04-Jan-19 | 05-Jan-19 | 06-Jan-19 | 07-Jan-19 | 08-Jan-19 | 09-Jan-19 | 10-Jan-19 | 11-Jan-19 | 12-Jan-19 | 13-Jan-19 | 14-Jan-19 | 15-Jan-19 | 16-Jan-19 | 17-Jan-19 | 18-Jan-19 | 19-Jan-19 | 20-Jan-19 | 21-Jan-19 | 22-Jan-19 | 23-Jan-19 | 24-Jan-19 | 25-Jan-19 | 26-Jan-19 | 27-Jan-19 | 28-Jan-19 | 29-Jan-19 | 30-Jan-19 | 31-Jan-19 | 01-Feb-19 | 02-Feb-19 | 03-Feb-19 | 04-Feb-19 | 05-Feb-19 | 06-Feb-19 | 07-Feb-19 | 08-Feb-19 | 09-Feb-19 | 10-Feb-19 | 11-Feb-19 | 12-Feb-19 | 13-Feb-19 | 14-Feb-19 | 15-Feb-19 | 16-Feb-19 | 17-Feb-19 | 18-Feb-19 | 19-Feb-19 | 20-Feb-19 | 21-Feb-19 | 22-Feb-19 | 23-Feb-19 | 24-Feb-19 | 25-Feb-19 | 26-Feb-19 | 27-Feb-19 | 28-Feb-19 | 01-Mar-19 | 02-Mar-19 | 03-Mar-19 | 04-Mar-19 | 05-Mar-19 | 06-Mar-19 | 07-Mar-19 | 08-Mar-19 | 09-Mar-19 | 10-Mar-19 | 11-Mar-19 | 12-Mar-19 | 13-Mar-19 | 14-Mar-19 | 15-Mar-19 | 16-Mar-19 | 17-Mar-19 | 18-Mar-19 | 19-Mar-19 | 20-Mar-19 | 21-Mar-19 | 22-Mar-19 | 23-Mar-19 | 24-Mar-19 | 25-Mar-19 | 26-Mar-19 | 27-Mar-19 | 28-Mar-19 | 29-Mar-19
A1010 | Mobilization and Site Office Installation | Cost-School | Cost-School | 990000 | 990000 | Budgeted Units | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000
A1010 | Mobilization and Site Office Installation | Cost-School | Cost-School | 990000 | 990000 | Budgeted Cost | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000
A1030 | Excavation Works | Cost-School | Cost-School | 1342000 | 1342000 | Budgeted Units | [30 empty] | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680
A1030 | Excavation Works | Cost-School | Cost-School | 1342000 | 1342000 | Budgeted Cost | [30 empty] | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680
E1070 | Fence Works | Cost-School | Cost-School | 4840000 | 4840000 | Budgeted Units | [323 empty] | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800
E1070 | Fence Works | Cost-School | Cost-School | 4840000 | 4840000 | Budgeted Cost | [323 empty] | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800
E1071 | External Tiling Works | Cost-School | Cost-School | 880000 | 880000 | Budgeted Units | [373 empty] | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200
E1071 | External Tiling Works | Cost-School | Cost-School | 880000 | 880000 | Budgeted Cost | [373 empty] | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Cost-School | Cost-School | 1669800 | 1669800 | Budgeted Units | [170 empty] | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Cost-School | Cost-School | 1669800 | 1669800 | Budgeted Cost | [170 empty] | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980 | 166980
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Cost-School | Cost-School | 4569400 | 4569400 | Budgeted Units | [207 empty] | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Cost-School | Cost-School | 4569400 | 4569400 | Budgeted Cost | [207 empty] | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313 | 152313
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Cost-School | Cost-School | 5618800 | 5618800 | Budgeted Units | [283 empty] | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Cost-School | Cost-School | 5618800 | 5618800 | Budgeted Cost | [283 empty] | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470
A1050 | Foundation Works | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Units | [55 empty] | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56
A1050 | Foundation Works | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Cost | [55 empty] | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156 | 59156
A1210 | Ground Floor Slab | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Units | [100 empty] | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100
A1210 | Ground Floor Slab | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Cost | [100 empty] | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100
A1220 | Ground Floor Columns | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Units | [120 empty] | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67
A1220 | Ground Floor Columns | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Cost | [120 empty] | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467 | 177467
A1230 | Roof Slab | Cost-School | Cost-School | 1342000 | 1342000 | Budgeted Units | [135 empty] | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67
A1230 | Roof Slab | Cost-School | Cost-School | 1342000 | 1342000 | Budgeted Cost | [135 empty] | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467 | 89467
A1240 | Parapet | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Units | [150 empty] | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33
A1240 | Parapet | Cost-School | Cost-School | 2662000 | 2662000 | Budgeted Cost | [150 empty] | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833 | 221833
A1250 | Block Works | Cost-School | Cost-School | 2186800 | 2186800 | Budgeted Units | [150 empty] | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340
A1250 | Block Works | Cost-School | Cost-School | 2186800 | 2186800 | Budgeted Cost | [150 empty] | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340
A1260 | Plaster | Cost-School | Cost-School | 2640000 | 2640000 | Budgeted Units | [180 empty] | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000
A1260 | Plaster | Cost-School | Cost-School | 2640000 | 2640000 | Budgeted Cost | [180 empty] | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000
A1270 | Ceramic | Cost-School | Cost-School | 2640000 | 2640000 | Budgeted Units | [195 empty] | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000
A1270 | Ceramic | Cost-School | Cost-School | 2640000 | 2640000 | Budgeted Cost | [195 empty] | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000
A1280 | Ceiling Works | Cost-School | Cost-School | 2860000 | 2860000 | Budgeted Units | [237 empty] | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33
A1280 | Ceiling Works | Cost-School | Cost-School | 2860000 | 2860000 | Budgeted Cost | [237 empty] | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333 | 95333
A1290 | Painting - 1st Coat | Cost-School | Cost-School | 6820000 | 6820000 | Budgeted Units | [273 empty] | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000
A1290 | Painting - 1st Coat | Cost-School | Cost-School | 6820000 | 6820000 | Budgeted Cost | [273 empty] | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000
A1310 | Plaster | Cost-School | Cost-School | 22000 | 22000 | Budgeted Units | [195 empty] | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200
A1310 | Plaster | Cost-School | Cost-School | 22000 | 22000 | Budgeted Cost | [195 empty] | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200
A1320 | Painting | Cost-School | Cost-School | 3080 | 3080 | Budgeted Units | [205 empty] | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33
A1320 | Painting | Cost-School | Cost-School | 3080 | 3080 | Budgeted Cost | [205 empty] | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205 | 205
A1300 | Doors and windows Works | Cost-School | Cost-School | 3960000 | 3960000 | Budgeted Units | [207 empty] | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000
A1300 | Doors and windows Works | Cost-School | Cost-School | 3960000 | 3960000 | Budgeted Cost | [207 empty] | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000 | 264000
E1081 | Green Area Works | Cost-School | Cost-School | 0 | 0 | Budgeted Units
E1081 | Green Area Works | Cost-School | Cost-School | 0 | 0 | Budgeted Cost
A1010 | Mobilization and Site Office Installation | Man-Power | Man-Power | 96 | 0 | Budgeted Units | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2 | 3.2
A1010 | Mobilization and Site Office Installation | Man-Power | Man-Power | 96 | 0 | Budgeted Cost
A1030 | Excavation Works | Man-Power | Man-Power | 250 | 0 | Budgeted Units | [30 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
A1030 | Excavation Works | Man-Power | Man-Power | 250 | 0 | Budgeted Cost
A1080 | Project Handing Over and Authority approvals | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [433 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
A1080 | Project Handing Over and Authority approvals | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
E1070 | Fence Works | Man-Power | Man-Power | 600 | 0 | Budgeted Units | [323 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
E1070 | Fence Works | Man-Power | Man-Power | 600 | 0 | Budgeted Cost
E1071 | External Tiling Works | Man-Power | Man-Power | 250 | 0 | Budgeted Units | [373 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
E1071 | External Tiling Works | Man-Power | Man-Power | 250 | 0 | Budgeted Cost
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Man-Power | Man-Power | 450 | 0 | Budgeted Units | [170 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Man-Power | Man-Power | 450 | 0 | Budgeted Cost
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Man-Power | Man-Power | 964 | 0 | Budgeted Units | [207 empty] | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Man-Power | Man-Power | 964 | 0 | Budgeted Cost
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Man-Power | Man-Power | 800 | 0 | Budgeted Units | [283 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Man-Power | Man-Power | 800 | 0 | Budgeted Cost
A1050 | Foundation Works | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [55 empty] | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22
A1050 | Foundation Works | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
A1210 | Ground Floor Slab | Man-Power | Man-Power | 346 | 0 | Budgeted Units | [100 empty] | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3
A1210 | Ground Floor Slab | Man-Power | Man-Power | 346 | 0 | Budgeted Cost
A1220 | Ground Floor Columns | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [120 empty] | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33
A1220 | Ground Floor Columns | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
A1230 | Roof Slab | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [135 empty] | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33
A1230 | Roof Slab | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
A1240 | Parapet | Man-Power | Man-Power | 184 | 0 | Budgeted Units | [150 empty] | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33
A1240 | Parapet | Man-Power | Man-Power | 184 | 0 | Budgeted Cost
A1250 | Block Works | Man-Power | Man-Power | 200 | 0 | Budgeted Units | [150 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
A1250 | Block Works | Man-Power | Man-Power | 200 | 0 | Budgeted Cost
A1260 | Plaster | Man-Power | Man-Power | 312 | 0 | Budgeted Units | [180 empty] | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8
A1260 | Plaster | Man-Power | Man-Power | 312 | 0 | Budgeted Cost
A1270 | Ceramic | Man-Power | Man-Power | 412.8 | 0 | Budgeted Units | [195 empty] | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4
A1270 | Ceramic | Man-Power | Man-Power | 412.8 | 0 | Budgeted Cost
A1280 | Ceiling Works | Man-Power | Man-Power | 314 | 0 | Budgeted Units | [237 empty] | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47
A1280 | Ceiling Works | Man-Power | Man-Power | 314 | 0 | Budgeted Cost
A1290 | Painting - 1st Coat | Man-Power | Man-Power | 488 | 0 | Budgeted Units | [273 empty] | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8
A1290 | Painting - 1st Coat | Man-Power | Man-Power | 488 | 0 | Budgeted Cost
A1310 | Plaster | Man-Power | Man-Power | 115.2 | 0 | Budgeted Units | [195 empty] | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52
A1310 | Plaster | Man-Power | Man-Power | 115.2 | 0 | Budgeted Cost
A1320 | Painting | Man-Power | Man-Power | 96 | 0 | Budgeted Units | [205 empty] | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4
A1320 | Painting | Man-Power | Man-Power | 96 | 0 | Budgeted Cost
A1300 | Doors and windows Works | Man-Power | Man-Power | 201.6 | 0 | Budgeted Units | [207 empty] | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44
A1300 | Doors and windows Works | Man-Power | Man-Power | 201.6 | 0 | Budgeted Cost
E1081 | Green Area Works | Man-Power | Man-Power | 46 | 0 | Budgeted Units | [381 empty] | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15
E1081 | Green Area Works | Man-Power | Man-Power | 46 | 0 | Budgeted Cost
A1410 | Roof Waterproofing woks | Cost-School | Cost-School | 2200 | 2200 | Budgeted Units | [150 empty] | 440 | 440 | 440 | 440 | 440
A1410 | Roof Waterproofing woks | Cost-School | Cost-School | 2200 | 2200 | Budgeted Cost | [150 empty] | 440 | 440 | 440 | 440 | 440
E1080 | Installation of Wheel Stopper & Corner Gaurd | Cost-School | Cost-School | 2420000 | 2420000 | Budgeted Units | [373 empty] | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33
E1080 | Installation of Wheel Stopper & Corner Gaurd | Cost-School | Cost-School | 2420000 | 2420000 | Budgeted Cost | [373 empty] | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333 | 40333
A1340 | Epoxy Coating-Services Area | Cost-School | Cost-School | 3960000 | 3960000 | Budgeted Units | [222 empty] | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000
A1340 | Epoxy Coating-Services Area | Cost-School | Cost-School | 3960000 | 3960000 | Budgeted Cost | [222 empty] | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000
A1350 | Kitchen Cabinets | Cost-School | Cost-School | 3740000 | 3740000 | Budgeted Units | [252 empty] | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67 | 311666.67
A1350 | Kitchen Cabinets | Cost-School | Cost-School | 3740000 | 3740000 | Budgeted Cost | [252 empty] | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667 | 311667
A1360 | Vanity Counter | Cost-School | Cost-School | 2860000 | 2860000 | Budgeted Units | [264 empty] | 715000 | 715000 | 715000 | 715000
A1360 | Vanity Counter | Cost-School | Cost-School | 2860000 | 2860000 | Budgeted Cost | [264 empty] | 715000 | 715000 | 715000 | 715000
A1370 | Wooden Doors | Cost-School | Cost-School | 1540000 | 1540000 | Budgeted Units | [268 empty] | 308000 | 308000 | 308000 | 308000 | 308000
A1370 | Wooden Doors | Cost-School | Cost-School | 1540000 | 1540000 | Budgeted Cost | [268 empty] | 308000 | 308000 | 308000 | 308000 | 308000
A1380 | Wardrobes | Cost-School | Cost-School | 6160000 | 6160000 | Budgeted Units | [303 empty] | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200
A1380 | Wardrobes | Cost-School | Cost-School | 6160000 | 6160000 | Budgeted Cost | [303 empty] | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200
A1390 | Mirrors & Bath Accessories | Cost-School | Cost-School | 880000 | 880000 | Budgeted Units | [356 empty] | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000
A1390 | Mirrors & Bath Accessories | Cost-School | Cost-School | 880000 | 880000 | Budgeted Cost | [356 empty] | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000
A1330 | Painting Final Coat | Cost-School | Cost-School | 440000 | 440000 | Budgeted Units | [348 empty] | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000
A1330 | Painting Final Coat | Cost-School | Cost-School | 440000 | 440000 | Budgeted Cost | [348 empty] | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000
A1400 | Balcony Handrails | Cost-School | Cost-School | 1320 | 1320 | Budgeted Units | [205 empty] | 264 | 264 | 264 | 264 | 264
A1400 | Balcony Handrails | Cost-School | Cost-School | 1320 | 1320 | Budgeted Cost | [205 empty] | 264 | 264 | 264 | 264 | 264
1-SUB-100 | Concrete | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [10 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-100 | Concrete | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-110 | Block | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-110 | Block | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-120 | Ceramic | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [100 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-120 | Ceramic | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-130 | Doors and window | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [100 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-130 | Doors and window | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-140 | Wood Works | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [120 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-140 | Wood Works | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-150 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-150 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-160 | Electrical | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-160 | Electrical | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-170 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-170 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-180 | Mirrors & Bath Accessories | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [120 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-180 | Mirrors & Bath Accessories | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-190 | Landscaping | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [220 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-190 | Landscaping | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SUB-200 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-200 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
2-MS1000 | Concrete | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [17 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1000 | Concrete | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1010 | Block | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [57 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1010 | Block | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1020 | Ceramic | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [107 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1020 | Ceramic | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1030 | Doors and window | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [107 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1030 | Doors and window | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [127 empty] | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29
2-MS1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
2-MS1050 | AC Machine | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [57 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1050 | AC Machine | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1060 | Electrical | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [57 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1060 | Electrical | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1070 | Plumbing | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [57 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1070 | Plumbing | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
2-MS1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 11.52 | 0 | Budgeted Units | [127 empty] | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65
2-MS1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 11.52 | 0 | Budgeted Cost
2-MS1090 | Landscaping | Man-Power | Man-Power | 150 | 0 | Budgeted Units | [227 empty] | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43
2-MS1090 | Landscaping | Man-Power | Man-Power | 150 | 0 | Budgeted Cost
2-MS1100 | Fire Fighting | Man-Power | Man-Power | 23.04 | 0 | Budgeted Units | [57 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1100 | Fire Fighting | Man-Power | Man-Power | 23.04 | 0 | Budgeted Cost
3-MA1000 | Concrete | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [24 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1000 | Concrete | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1010 | Block | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [64 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1010 | Block | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1020 | Ceramic | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [114 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1020 | Ceramic | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1030 | Doors and window | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [114 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1030 | Doors and window | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [134 empty] | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29
3-MA1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
3-MA1050 | AC Machine | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [64 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1050 | AC Machine | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1060 | Electrical | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [64 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1060 | Electrical | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1070 | Plumbing | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [64 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1070 | Plumbing | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [134 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
3-MA1090 | Landscaping | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [234 empty] | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29
3-MA1090 | Landscaping | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
3-MA1100 | Fire Fighting | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [64 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1100 | Fire Fighting | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
4-MD1000 | Concrete | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [31 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
4-MD1000 | Concrete | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
4-MD1010 | Block | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [71 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
4-MD1010 | Block | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
4-MD1020 | Ceramic | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [121 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
4-MD1020 | Ceramic | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
4-MD1030 | Doors and window | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [121 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
4-MD1030 | Doors and window | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
4-MD1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [141 empty] | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67
4-MD1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
4-MD1050 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [71 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1050 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
4-MD1060 | Electrical | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [71 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1060 | Electrical | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
4-MD1070 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [71 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1070 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
4-MD1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 8 | 0 | Budgeted Units | [141 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 8 | 0 | Budgeted Cost
4-MD1090 | Landscaping | Man-Power | Man-Power | 200 | 0 | Budgeted Units | [241 empty] | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33
4-MD1090 | Landscaping | Man-Power | Man-Power | 200 | 0 | Budgeted Cost
4-MD1100 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | Budgeted Units | [71 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1100 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | Budgeted Cost
1-SDS100 | Structural Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [60 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43
1-SDS100 | Structural Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
1-SDS110 | Finishes Drawings | Man-Power | Man-Power | 123 | 0 | Budgeted Units | [100 empty] | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79
1-SDS110 | Finishes Drawings | Man-Power | Man-Power | 123 | 0 | Budgeted Cost
1-SDS120 | Mechanical Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [120 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43
1-SDS120 | Mechanical Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
1-SDS130 | Electrical Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [120 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43
1-SDS130 | Electrical Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
1-SDS140 | Fire Fighting Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [120 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43
1-SDS140 | Fire Fighting Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
1-SDS150 | Plumbing Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Units | [120 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43
1-SDS150 | Plumbing Drawings | Man-Power | Man-Power | 20 | 0 | Budgeted Cost
2-SDA1000 | Structural Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [74 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1000 | Structural Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
2-SDA1010 | Finishes Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [114 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1010 | Finishes Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
2-SDA1020 | Mechanical Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [134 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1020 | Mechanical Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
2-SDA1030 | Electrical Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [134 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1030 | Electrical Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
2-SDA1040 | Fire Fighting Drawings | Man-Power | Man-Power | 15.36 | 0 | Budgeted Units | [134 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
2-SDA1040 | Fire Fighting Drawings | Man-Power | Man-Power | 15.36 | 0 | Budgeted Cost
2-SDA1050 | Plumbing Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Units | [134 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1050 | Plumbing Drawings | Man-Power | Man-Power | 61.44 | 0 | Budgeted Cost
E1080 | Installation of Wheel Stopper & Corner Gaurd | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [373 empty] | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67
E1080 | Installation of Wheel Stopper & Corner Gaurd | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
A1400 | Balcony Handrails | Man-Power | Man-Power | 24 | 0 | Budgeted Units | [205 empty] | 4.8 | 4.8 | 4.8 | 4.8 | 4.8
A1400 | Balcony Handrails | Man-Power | Man-Power | 24 | 0 | Budgeted Cost
A1410 | Roof Waterproofing woks | Man-Power | Man-Power | 100 | 0 | Budgeted Units | [150 empty] | 20 | 20 | 20 | 20 | 20
A1410 | Roof Waterproofing woks | Man-Power | Man-Power | 100 | 0 | Budgeted Cost
A1390 | Mirrors & Bath Accessories | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [356 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
A1390 | Mirrors & Bath Accessories | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
A1330 | Painting Final Coat | Man-Power | Man-Power | 50 | 0 | Budgeted Units | [348 empty] | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25
A1330 | Painting Final Coat | Man-Power | Man-Power | 50 | 0 | Budgeted Cost
A1380 | Wardrobes | Man-Power | Man-Power | 688 | 0 | Budgeted Units | [303 empty] | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76
A1380 | Wardrobes | Man-Power | Man-Power | 688 | 0 | Budgeted Cost
A1370 | Wooden Doors | Man-Power | Man-Power | 300 | 0 | Budgeted Units | [268 empty] | 60 | 60 | 60 | 60 | 60
A1370 | Wooden Doors | Man-Power | Man-Power | 300 | 0 | Budgeted Cost
A1360 | Vanity Counter | Man-Power | Man-Power | 300 | 0 | Budgeted Units | [264 empty] | 75 | 75 | 75 | 75
A1360 | Vanity Counter | Man-Power | Man-Power | 300 | 0 | Budgeted Cost
A1350 | Kitchen Cabinets | Man-Power | Man-Power | 316 | 0 | Budgeted Units | [252 empty] | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33 | 26.33
A1350 | Kitchen Cabinets | Man-Power | Man-Power | 316 | 0 | Budgeted Cost
A1340 | Epoxy Coating-Services Area | Man-Power | Man-Power | 120 | 0 | Budgeted Units | [222 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A1340 | Epoxy Coating-Services Area | Man-Power | Man-Power | 120 | 0 | Budgeted Cost
HOV110 | Submission of As Built Drawings | Man-Power | Man-Power | 24 | 0 | Budgeted Units | [363 empty] | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4
HOV110 | Submission of As Built Drawings | Man-Power | Man-Power | 24 | 0 | Budgeted Cost
HOV110 | Submission of As Built Drawings | Cost-School | Cost-School | 22000 | 22000 | Budgeted Units | [363 empty] | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200
HOV110 | Submission of As Built Drawings | Cost-School | Cost-School | 22000 | 22000 | Budgeted Cost | [363 empty] | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200
A1080 | Project Handing Over and Authority approvals | Cost-School | Cost-School | 8800 | 8800 | Budgeted Units | [433 empty] | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440
A1080 | Project Handing Over and Authority approvals | Cost-School | Cost-School | 8800 | 8800 | Budgeted Cost | [433 empty] | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440

## UP-Activities
Activity ID | Activity Name | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | BL1 Start | BL1 Finish | Total Float | Activity % Complete | Activity Type | L01 | L02 | L03 | L04
A1010 | Mobilization and Site Office Installation | 30 | 1 | 281 | 2018-01-01 |  | 01-Jan-18 A | 2018-10-09 | 2018-01-01 | 2018-01-30 | 0 | 96.67% | Task Dependent | L01-01 | (New)-1 | (New)-1 | (New)-1
KEY-16 | Project Start Date | 0 | 0 | 0 | 2018-01-01 |  | 01-Jan-18 A |  | 2018-01-01 |  |  | 100% | Start Milestone | L01-01 | (New) | (New) | (New)
2-MS1060 | Electrical | 7 | 0 | 7 | 2018-01-07 | 2018-01-13 | 07-Jan-18 A | 13-Jan-18 A | 2018-02-27 | 2018-03-05 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1000 | Concrete | 7 | 0 | 107 | 2018-01-07 | 2018-04-24 | 07-Jan-18 A | 24-Apr-18 A | 2018-01-25 | 2018-01-31 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
2-MS1030 | Doors and window | 7 | 0 | 10 | 2018-01-07 | 2018-01-17 | 07-Jan-18 A | 17-Jan-18 A | 2018-04-18 | 2018-04-24 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1040 | Wood Works | 7 | 0 | 7 | 2018-01-07 | 2018-01-13 | 07-Jan-18 A | 13-Jan-18 A | 2018-05-08 | 2018-05-14 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1070 | Plumbing | 7 | 3.5 | 275 | 2018-01-07 |  | 07-Jan-18 A | 2018-10-12 | 2018-02-27 | 2018-03-05 | 61.5 | 50% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
A1030 | Excavation Works | 25 | 0 | 25 | 2018-01-08 | 2018-02-01 | 08-Jan-18 A | 01-Feb-18 A | 2018-01-31 | 2018-02-24 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-8
2-MS1000 | Concrete | 7 | 0 | 40 | 2018-01-09 | 2018-02-18 | 09-Jan-18 A | 18-Feb-18 A | 2018-01-18 | 2018-01-24 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1010 | Block | 7 | 0 | 22 | 2018-01-09 | 2018-01-31 | 09-Jan-18 A | 31-Jan-18 A | 2018-02-27 | 2018-03-05 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1020 | Ceramic | 7 | 0 | 1 | 2018-01-09 | 2018-01-10 | 09-Jan-18 A | 10-Jan-18 A | 2018-04-18 | 2018-04-24 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
1-SUB-100 | Concrete | 7 | 0 | 7 | 2018-01-11 | 2018-01-17 | 11-Jan-18 A | 17-Jan-18 A | 2018-01-11 | 2018-01-17 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
4-MD1000 | Concrete | 7 | 0 | 12 | 2018-01-16 | 2018-01-27 | 16-Jan-18 A | 27-Jan-18 A | 2018-02-01 | 2018-02-07 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1030 | Doors and window | 60 | 0 | 60 | 2018-01-21 | 2018-03-21 | 21-Jan-18 A | 21-Mar-18 A | 2018-05-02 | 2018-06-30 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1040 | Wood Works | 60 | 6 | 261 | 2018-01-21 |  | 21-Jan-18 A | 2018-10-14 | 2018-05-22 | 2018-07-20 | 62 | 90% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1050 | AC Machine | 60 | 3 | 261 | 2018-01-21 |  | 21-Jan-18 A | 2018-10-11 | 2018-03-13 | 2018-05-11 | 68 | 95% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1060 | Electrical | 60 | 6 | 261 | 2018-01-21 |  | 21-Jan-18 A | 2018-10-14 | 2018-03-13 | 2018-05-11 | 65 | 90% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1070 | Plumbing | 60 | 6 | 261 | 2018-01-21 |  | 21-Jan-18 A | 2018-10-18 | 2018-03-13 | 2018-05-11 | 61.5 | 90% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1100 | Fire Fighting | 60 | 12 | 261 | 2018-01-21 |  | 21-Jan-18 A | 2018-10-27 | 2018-03-13 | 2018-05-11 | 52 | 80% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1010 | Block | 7 | 0 | 9 | 2018-01-22 | 2018-01-31 | 22-Jan-18 A | 31-Jan-18 A | 2018-03-13 | 2018-03-19 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
3-MA1010 | Block | 7 | 0 | 55 | 2018-01-23 | 2018-03-19 | 23-Jan-18 A | 19-Mar-18 A | 2018-03-06 | 2018-03-12 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1030 | Doors and window | 7 | 0 | 0.7 | 2018-01-23 | 2018-01-23 | 23-Jan-18 A | 23-Jan-18 A | 2018-04-25 | 2018-05-01 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1040 | Wood Works | 7 | 0 | 0.7 | 2018-01-23 | 2018-01-23 | 23-Jan-18 A | 23-Jan-18 A | 2018-05-15 | 2018-05-21 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1050 | AC Machine | 7 | 0 | 59 | 2018-01-23 | 2018-03-23 | 23-Jan-18 A | 23-Mar-18 A | 2018-03-06 | 2018-03-12 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1070 | Plumbing | 7 | 0 | 65 | 2018-01-23 | 2018-03-29 | 23-Jan-18 A | 29-Mar-18 A | 2018-03-06 | 2018-03-12 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
4-MD1020 | Ceramic | 60 | 12 | 259 | 2018-01-23 |  | 23-Jan-18 A | 2018-10-20 | 2018-05-02 | 2018-06-30 | 56 | 80% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
3-MA1020 | Ceramic | 7 | 0 | 0.7 | 2018-01-24 | 2018-01-24 | 24-Jan-18 A | 24-Jan-18 A | 2018-04-25 | 2018-05-01 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1060 | Electrical | 7 | 0 | 55 | 2018-01-24 | 2018-03-20 | 24-Jan-18 A | 20-Mar-18 A | 2018-03-06 | 2018-03-12 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1100 | Fire Fighting | 7 | 0 | 55 | 2018-01-24 | 2018-03-20 | 24-Jan-18 A | 20-Mar-18 A | 2018-03-06 | 2018-03-12 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
KEY-26 | Start Construction | 0 | 0 | 0 | 2018-01-31 |  | 31-Jan-18 A |  | 2018-01-31 |  |  | 100% | Start Milestone | L01-01 | (New) | (New) | (New)
A1050 | Foundation Works | 45 | 45 | 249 | 2018-02-02 |  | 02-Feb-18 A | 2018-11-23 | 2018-02-25 | 2018-04-10 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-8
1-SUB-110 | Block | 7 | 0 | 7 | 2018-02-20 | 2018-02-26 | 20-Feb-18 A | 26-Feb-18 A | 2018-02-20 | 2018-02-26 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-150 | AC Machine | 7 | 0 | 7 | 2018-02-20 | 2018-02-26 | 20-Feb-18 A | 26-Feb-18 A | 2018-02-20 | 2018-02-26 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-160 | Electrical | 7 | 0 | 7 | 2018-02-20 | 2018-02-26 | 20-Feb-18 A | 26-Feb-18 A | 2018-02-20 | 2018-02-26 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-170 | Plumbing | 7 | 0 | 7 | 2018-02-20 | 2018-02-26 | 20-Feb-18 A | 26-Feb-18 A | 2018-02-20 | 2018-02-26 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-200 | Fire Fighting | 7 | 0 | 7 | 2018-02-20 | 2018-02-26 | 20-Feb-18 A | 26-Feb-18 A | 2018-02-20 | 2018-02-26 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
2-MS1050 | AC Machine | 7 | 0 | 6 | 2018-03-07 | 2018-03-13 | 07-Mar-18 A | 13-Mar-18 A | 2018-02-27 | 2018-03-05 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
1-SDS100 | Structural Drawings | 14 | 0 | 18 | 2018-03-11 | 2018-03-29 | 11-Mar-18 A | 29-Mar-18 A | 2018-03-02 | 2018-03-15 |  | 100% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
2-SDA1000 | Structural Drawings | 14 | 0 | 14 | 2018-03-16 | 2018-03-29 | 16-Mar-18 A | 29-Mar-18 A | 2018-03-16 | 2018-03-29 |  | 100% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
1-SUB-120 | Ceramic | 7 | 0 | 7 | 2018-04-11 | 2018-04-17 | 11-Apr-18 A | 17-Apr-18 A | 2018-04-11 | 2018-04-17 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
1-SUB-130 | Doors and window | 7 | 0 | 7 | 2018-04-11 | 2018-04-17 | 11-Apr-18 A | 17-Apr-18 A | 2018-04-11 | 2018-04-17 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
A1210 | Ground Floor Slab | 20 | 20 | 177 | 2018-04-15 |  | 15-Apr-18 A | 2018-12-13 | 2018-04-11 | 2018-04-30 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-9
1-SDS110 | Finishes Drawings | 14 | 0 | 14 | 2018-04-18 | 2018-05-01 | 18-Apr-18 A | 01-May-18 A | 2018-04-11 | 2018-04-24 |  | 100% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
2-SDA1010 | Finishes Drawings | 14 | 0 | 14 | 2018-04-25 | 2018-05-08 | 25-Apr-18 A | 08-May-18 A | 2018-04-25 | 2018-05-08 |  | 100% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
1-SUB-140 | Wood Works | 7 | 0 | 7 | 2018-05-01 | 2018-05-07 | 01-May-18 A | 07-May-18 A | 2018-05-01 | 2018-05-07 |  | 100% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
A1220 | Ground Floor Columns | 15 | 0 | 15 | 2018-05-12 | 2018-05-26 | 12-May-18 A | 26-May-18 A | 2018-05-01 | 2018-05-15 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-9
1-SDS120 | Mechanical Drawings | 14 | 2.8 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-11 | 2018-05-01 | 2018-05-14 | 65.4 | 80% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
1-SDS130 | Electrical Drawings | 14 | 2.8 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-11 | 2018-05-01 | 2018-05-14 | 61.2 | 80% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
1-SDS150 | Plumbing Drawings | 14 | 2.8 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-11 | 2018-05-01 | 2018-05-14 | 59.8 | 80% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
2-SDA1020 | Mechanical Drawings | 14 | 2.8 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-14 | 2018-05-15 | 2018-05-28 | 65.4 | 80% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1030 | Electrical Drawings | 14 | 7 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-18 | 2018-05-15 | 2018-05-28 | 61.2 | 50% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1040 | Fire Fighting Drawings | 14 | 7 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-27 | 2018-05-15 | 2018-05-28 | 52.8 | 50% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
2-SDA1050 | Plumbing Drawings | 14 | 8.4 | 147 | 2018-05-15 |  | 15-May-18 A | 2018-10-20 | 2018-05-15 | 2018-05-28 | 59.8 | 40% | Task Dependent | L01-01 | (New)-3 | (New)-7 | (New)-7
1-SDS140 | Fire Fighting Drawings | 14 | 11.2 | 140 | 2018-05-22 |  | 22-May-18 A | 2018-10-20 | 2018-05-01 | 2018-05-14 | 52.8 | 20% | Task Dependent | L01-01 | (New)-3 | (New)-6 | (New)-6
A1230 | Roof Slab | 15 | 0 | 15 | 2018-05-26 | 2018-06-09 | 26-May-18 A | 09-Jun-18 A | 2018-05-16 | 2018-05-30 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-10
A1250 | Block Works | 20 | 0 | 20 | 2018-06-09 | 2018-06-28 | 09-Jun-18 A | 28-Jun-18 A | 2018-05-31 | 2018-06-19 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1270 | Ceramic | 12 | 0 | 12 | 2018-07-03 | 2018-07-14 | 03-Jul-18 A | 14-Jul-18 A | 2018-07-15 | 2018-07-26 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1410 | Roof Waterproofing woks | 5 | 0 | 36 | 2018-07-04 | 2018-08-08 | 04-Jul-18 A | 08-Aug-18 A | 2018-05-31 | 2018-06-04 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1260 | Plaster | 15 | 0 | 15 | 2018-07-09 | 2018-07-23 | 09-Jul-18 A | 23-Jul-18 A | 2018-06-30 | 2018-07-14 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | 10 | 2 | 66 | 2018-08-04 |  | 04-Aug-18 A | 2018-12-15 | 2018-06-20 | 2018-06-29 | 0 | 80% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
1-SUB-190 | Landscaping | 7 | 7 | 61 | 2018-08-09 |  | 09-Aug-18 A | 2018-10-15 | 2018-08-09 | 2018-08-15 | 42 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | 30 | 6 | 56 | 2018-08-14 |  | 14-Aug-18 A | 2018-12-21 | 2018-07-27 | 2018-08-25 | 3 | 80% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
A1280 | Ceiling Works | 30 | 0 | 30 | 2018-08-14 | 2018-09-12 | 14-Aug-18 A | 12-Sep-18 A | 2018-08-26 | 2018-09-24 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1300 | Doors and windows Works | 15 | 0 | 17 | 2018-08-14 | 2018-08-31 | 14-Aug-18 A | 31-Aug-18 A | 2018-07-27 | 2018-08-10 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1310 | Plaster | 10 | 0 | 10 | 2018-08-16 | 2018-08-25 | 16-Aug-18 A | 25-Aug-18 A | 2018-07-15 | 2018-07-24 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
A1340 | Epoxy Coating-Services Area | 30 | 0 | 60 | 2018-08-31 | 2018-10-29 | 31-Aug-18 A | 29-Oct-18 A | 2018-08-11 | 2018-09-09 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1290 | Painting - 1st Coat | 10 | 0 | 10 | 2018-09-19 | 2018-09-28 | 19-Sep-18 A | 28-Sep-18 A | 2018-10-01 | 2018-10-10 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1350 | Kitchen Cabinets | 12 | 0 | 20 | 2018-09-30 | 2018-10-19 | 30-Sep-18 A | 19-Oct-18 A | 2018-09-10 | 2018-09-21 |  | 100% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | 40 | 16 | 67 | 2018-10-19 |  | 19-Oct-18 A | 2019-01-09 | 2018-10-11 | 2018-11-19 | 0 | 60% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-13
KEY-46 | Completion of Construction For Villa Building | 0 | 0 | 0 |  | 2018-11-19 |  | 19-Nov-18 A |  | 2018-11-19 |  | 100% | Finish Milestone | L01-01 | (New) | (New) | (New)
E1070 | Fence Works | 50 | 10 | 43 | 2018-11-28 |  | 28-Nov-18 A | 2019-01-19 | 2018-11-20 | 2019-01-08 | 0 | 80% | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
E1071 | External Tiling Works | 25 | 12.5 | 3 | 2019-01-17 |  | 17-Jan-19 A | 2019-02-01 | 2019-01-09 | 2019-02-02 | 47.5 | 50% | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
A1080 | Project Handing Over and Authority approvals | 20 | 20 | 0 |  |  | 2019-03-21 | 2019-04-09 | 2019-03-10 | 2019-03-29 | 0 | 0% | Task Dependent | L01-01 | (New)-5 | (New)-10 | (New)-15
KEY-6 | Project Finish Date | 0 | 0 | 0 |  |  |  | 2019-04-09 |  | 2019-03-29 | 0 | 0% | Finish Milestone | L01-01 | (New) | (New) | (New)
A1240 | Parapet | 12 | 12 | 0 |  |  | 2018-12-14 | 2018-12-25 | 2018-05-31 | 2018-06-11 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-10
A1320 | Painting | 15 | 15 | 0 |  |  | 2018-12-26 | 2019-01-09 | 2018-07-25 | 2018-08-08 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
E1081 | Green Area Works | 40 | 40 | 0 |  |  | 2019-01-28 | 2019-03-08 | 2019-01-17 | 2019-02-25 | 12 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
KEY-36 | Start Construction For External Works | 0 | 0 | 0 |  |  | 2019-01-10 |  | 2018-11-20 |  | 0 | 0% | Start Milestone | L01-01 | (New) | (New) | (New)
KEY-56 | Completion of Construction For External Works | 0 | 0 | 0 |  |  |  | 2019-03-08 |  | 2019-02-25 | 12 | 0% | Finish Milestone | L01-01 | (New) | (New) | (New)
HOV110 | Submission of As Built Drawings | 10 | 10 | 0 |  |  | 2019-01-10 | 2019-01-19 | 2018-12-30 | 2019-01-08 | 60 | 0% | Task Dependent | L01-01 | (New)-5 | (New)-10 | (New)-15
E1080 | Installation of Wheel Stopper & Corner Gaurd | 60 | 60 | 0 |  |  | 2019-01-20 | 2019-03-20 | 2019-01-09 | 2019-03-09 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-9 | (New)-14
A1330 | Painting Final Coat | 8 | 8 | 0 |  |  | 2019-02-18 | 2019-02-25 | 2018-12-15 | 2018-12-22 | 3 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1360 | Vanity Counter | 4 | 4 | 0 |  |  | 2018-12-16 | 2018-12-19 | 2018-09-22 | 2018-09-25 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1370 | Wooden Doors | 5 | 5 | 0 |  |  | 2018-12-20 | 2018-12-24 | 2018-09-26 | 2018-09-30 | 0 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1380 | Wardrobes | 50 | 50 | 0 |  |  | 2019-01-04 | 2019-02-22 | 2018-10-31 | 2018-12-19 | 3 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1390 | Mirrors & Bath Accessories | 20 | 20 | 0 |  |  | 2019-02-26 | 2019-03-17 | 2018-12-23 | 2019-01-11 | 3 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-11
A1400 | Balcony Handrails | 5 | 5 | 0 |  |  | 2018-12-26 | 2018-12-30 | 2018-07-25 | 2018-07-29 | 80 | 0% | Task Dependent | L01-01 | (New)-4 | (New)-8 | (New)-12
1-SUB-180 | Mirrors & Bath Accessories | 7 | 7 | 0 |  |  | 2018-10-09 | 2018-10-15 | 2018-05-01 | 2018-05-07 | 62 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-2 | (New)-2
2-MS1080 | Mirrors & Bath Accessories | 7 | 7 | 0 |  |  | 2018-10-16 | 2018-10-22 | 2018-05-08 | 2018-05-14 | 62 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1090 | Landscaping | 7 | 7 | 0 |  |  | 2018-10-16 | 2018-10-22 | 2018-08-16 | 2018-08-22 | 42 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
2-MS1100 | Fire Fighting | 7 | 7 | 0 |  |  | 2018-10-09 | 2018-10-15 | 2018-02-27 | 2018-03-05 | 52 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-3 | (New)-3
3-MA1080 | Mirrors & Bath Accessories | 7 | 7 | 0 |  |  | 2018-10-23 | 2018-10-29 | 2018-05-15 | 2018-05-21 | 62 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
3-MA1090 | Landscaping | 7 | 7 | 0 |  |  | 2018-10-23 | 2018-10-29 | 2018-08-23 | 2018-08-29 | 42 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-4 | (New)-4
4-MD1080 | Mirrors & Bath Accessories | 60 | 60 | 0 |  |  | 2018-10-30 | 2018-12-28 | 2018-05-22 | 2018-07-20 | 62 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5
4-MD1090 | Landscaping | 60 | 60 | 0 |  |  | 2018-10-30 | 2018-12-28 | 2018-08-30 | 2018-10-28 | 42 | 0% | Task Dependent | L01-01 | (New)-2 | (New)-5 | (New)-5

## UP-Res
Activity ID | Activity Name | Resource ID | Resource Name | Budgeted Units | Budgeted Cost | Units % Complete | Actual Units | Spreadsheet Field | 01-Jan-18 | 02-Jan-18 | 03-Jan-18 | 04-Jan-18 | 05-Jan-18 | 06-Jan-18 | 07-Jan-18 | 08-Jan-18 | 09-Jan-18 | 10-Jan-18 | 11-Jan-18 | 12-Jan-18 | 13-Jan-18 | 14-Jan-18 | 15-Jan-18 | 16-Jan-18 | 17-Jan-18 | 18-Jan-18 | 19-Jan-18 | 20-Jan-18 | 21-Jan-18 | 22-Jan-18 | 23-Jan-18 | 24-Jan-18 | 25-Jan-18 | 26-Jan-18 | 27-Jan-18 | 28-Jan-18 | 29-Jan-18 | 30-Jan-18 | 31-Jan-18 | 01-Feb-18 | 02-Feb-18 | 03-Feb-18 | 04-Feb-18 | 05-Feb-18 | 06-Feb-18 | 07-Feb-18 | 08-Feb-18 | 09-Feb-18 | 10-Feb-18 | 11-Feb-18 | 12-Feb-18 | 13-Feb-18 | 14-Feb-18 | 15-Feb-18 | 16-Feb-18 | 17-Feb-18 | 18-Feb-18 | 19-Feb-18 | 20-Feb-18 | 21-Feb-18 | 22-Feb-18 | 23-Feb-18 | 24-Feb-18 | 25-Feb-18 | 26-Feb-18 | 27-Feb-18 | 28-Feb-18 | 01-Mar-18 | 02-Mar-18 | 03-Mar-18 | 04-Mar-18 | 05-Mar-18 | 06-Mar-18 | 07-Mar-18 | 08-Mar-18 | 09-Mar-18 | 10-Mar-18 | 11-Mar-18 | 12-Mar-18 | 13-Mar-18 | 14-Mar-18 | 15-Mar-18 | 16-Mar-18 | 17-Mar-18 | 18-Mar-18 | 19-Mar-18 | 20-Mar-18 | 21-Mar-18 | 22-Mar-18 | 23-Mar-18 | 24-Mar-18 | 25-Mar-18 | 26-Mar-18 | 27-Mar-18 | 28-Mar-18 | 29-Mar-18 | 30-Mar-18 | 31-Mar-18 | 01-Apr-18 | 02-Apr-18 | 03-Apr-18 | 04-Apr-18 | 05-Apr-18 | 06-Apr-18 | 07-Apr-18 | 08-Apr-18 | 09-Apr-18 | 10-Apr-18 | 11-Apr-18 | 12-Apr-18 | 13-Apr-18 | 14-Apr-18 | 15-Apr-18 | 16-Apr-18 | 17-Apr-18 | 18-Apr-18 | 19-Apr-18 | 20-Apr-18 | 21-Apr-18 | 22-Apr-18 | 23-Apr-18 | 24-Apr-18 | 25-Apr-18 | 26-Apr-18 | 27-Apr-18 | 28-Apr-18 | 29-Apr-18 | 30-Apr-18 | 01-May-18 | 02-May-18 | 03-May-18 | 04-May-18 | 05-May-18 | 06-May-18 | 07-May-18 | 08-May-18 | 09-May-18 | 10-May-18 | 11-May-18 | 12-May-18 | 13-May-18 | 14-May-18 | 15-May-18 | 16-May-18 | 17-May-18 | 18-May-18 | 19-May-18 | 20-May-18 | 21-May-18 | 22-May-18 | 23-May-18 | 24-May-18 | 25-May-18 | 26-May-18 | 27-May-18 | 28-May-18 | 29-May-18 | 30-May-18 | 31-May-18 | 01-Jun-18 | 02-Jun-18 | 03-Jun-18 | 04-Jun-18 | 05-Jun-18 | 06-Jun-18 | 07-Jun-18 | 08-Jun-18 | 09-Jun-18 | 10-Jun-18 | 11-Jun-18 | 12-Jun-18 | 13-Jun-18 | 14-Jun-18 | 15-Jun-18 | 16-Jun-18 | 17-Jun-18 | 18-Jun-18 | 19-Jun-18 | 20-Jun-18 | 21-Jun-18 | 22-Jun-18 | 23-Jun-18 | 24-Jun-18 | 25-Jun-18 | 26-Jun-18 | 27-Jun-18 | 28-Jun-18 | 29-Jun-18 | 30-Jun-18 | 01-Jul-18 | 02-Jul-18 | 03-Jul-18 | 04-Jul-18 | 05-Jul-18 | 06-Jul-18 | 07-Jul-18 | 08-Jul-18 | 09-Jul-18 | 10-Jul-18 | 11-Jul-18 | 12-Jul-18 | 13-Jul-18 | 14-Jul-18 | 15-Jul-18 | 16-Jul-18 | 17-Jul-18 | 18-Jul-18 | 19-Jul-18 | 20-Jul-18 | 21-Jul-18 | 22-Jul-18 | 23-Jul-18 | 24-Jul-18 | 25-Jul-18 | 26-Jul-18 | 27-Jul-18 | 28-Jul-18 | 29-Jul-18 | 30-Jul-18 | 31-Jul-18 | 01-Aug-18 | 02-Aug-18 | 03-Aug-18 | 04-Aug-18 | 05-Aug-18 | 06-Aug-18 | 07-Aug-18 | 08-Aug-18 | 09-Aug-18 | 10-Aug-18 | 11-Aug-18 | 12-Aug-18 | 13-Aug-18 | 14-Aug-18 | 15-Aug-18 | 16-Aug-18 | 17-Aug-18 | 18-Aug-18 | 19-Aug-18 | 20-Aug-18 | 21-Aug-18 | 22-Aug-18 | 23-Aug-18 | 24-Aug-18 | 25-Aug-18 | 26-Aug-18 | 27-Aug-18 | 28-Aug-18 | 29-Aug-18 | 30-Aug-18 | 31-Aug-18 | 01-Sep-18 | 02-Sep-18 | 03-Sep-18 | 04-Sep-18 | 05-Sep-18 | 06-Sep-18 | 07-Sep-18 | 08-Sep-18 | 09-Sep-18 | 10-Sep-18 | 11-Sep-18 | 12-Sep-18 | 13-Sep-18 | 14-Sep-18 | 15-Sep-18 | 16-Sep-18 | 17-Sep-18 | 18-Sep-18 | 19-Sep-18 | 20-Sep-18 | 21-Sep-18 | 22-Sep-18 | 23-Sep-18 | 24-Sep-18 | 25-Sep-18 | 26-Sep-18 | 27-Sep-18 | 28-Sep-18 | 29-Sep-18 | 30-Sep-18 | 01-Oct-18 | 02-Oct-18 | 03-Oct-18 | 04-Oct-18 | 05-Oct-18 | 06-Oct-18 | 07-Oct-18 | 08-Oct-18 | 09-Oct-18 | 10-Oct-18 | 11-Oct-18 | 12-Oct-18 | 13-Oct-18 | 14-Oct-18 | 15-Oct-18 | 16-Oct-18 | 17-Oct-18 | 18-Oct-18 | 19-Oct-18 | 20-Oct-18 | 21-Oct-18 | 22-Oct-18 | 23-Oct-18 | 24-Oct-18 | 25-Oct-18 | 26-Oct-18 | 27-Oct-18 | 28-Oct-18 | 29-Oct-18 | 30-Oct-18 | 31-Oct-18 | 01-Nov-18 | 02-Nov-18 | 03-Nov-18 | 04-Nov-18 | 05-Nov-18 | 06-Nov-18 | 07-Nov-18 | 08-Nov-18 | 09-Nov-18 | 10-Nov-18 | 11-Nov-18 | 12-Nov-18 | 13-Nov-18 | 14-Nov-18 | 15-Nov-18 | 16-Nov-18 | 17-Nov-18 | 18-Nov-18 | 19-Nov-18 | 20-Nov-18 | 21-Nov-18 | 22-Nov-18 | 23-Nov-18 | 24-Nov-18 | 25-Nov-18 | 26-Nov-18 | 27-Nov-18 | 28-Nov-18 | 29-Nov-18 | 30-Nov-18 | 01-Dec-18 | 02-Dec-18 | 03-Dec-18 | 04-Dec-18 | 05-Dec-18 | 06-Dec-18 | 07-Dec-18 | 08-Dec-18 | 09-Dec-18 | 10-Dec-18 | 11-Dec-18 | 12-Dec-18 | 13-Dec-18 | 14-Dec-18 | 15-Dec-18 | 16-Dec-18 | 17-Dec-18 | 18-Dec-18 | 19-Dec-18 | 20-Dec-18 | 21-Dec-18 | 22-Dec-18 | 23-Dec-18 | 24-Dec-18 | 25-Dec-18 | 26-Dec-18 | 27-Dec-18 | 28-Dec-18 | 29-Dec-18 | 30-Dec-18 | 31-Dec-18 | 01-Jan-19 | 02-Jan-19 | 03-Jan-19 | 04-Jan-19 | 05-Jan-19 | 06-Jan-19 | 07-Jan-19 | 08-Jan-19 | 09-Jan-19 | 10-Jan-19 | 11-Jan-19 | 12-Jan-19 | 13-Jan-19 | 14-Jan-19 | 15-Jan-19 | 16-Jan-19 | 17-Jan-19 | 18-Jan-19 | 19-Jan-19 | 20-Jan-19 | 21-Jan-19 | 22-Jan-19 | 23-Jan-19 | 24-Jan-19 | 25-Jan-19 | 26-Jan-19 | 27-Jan-19 | 28-Jan-19 | 29-Jan-19 | 30-Jan-19 | 31-Jan-19 | 01-Feb-19 | 02-Feb-19 | 03-Feb-19 | 04-Feb-19 | 05-Feb-19 | 06-Feb-19 | 07-Feb-19 | 08-Feb-19 | 09-Feb-19 | 10-Feb-19 | 11-Feb-19 | 12-Feb-19 | 13-Feb-19 | 14-Feb-19 | 15-Feb-19 | 16-Feb-19 | 17-Feb-19 | 18-Feb-19 | 19-Feb-19 | 20-Feb-19 | 21-Feb-19 | 22-Feb-19 | 23-Feb-19 | 24-Feb-19 | 25-Feb-19 | 26-Feb-19 | 27-Feb-19 | 28-Feb-19 | 01-Mar-19 | 02-Mar-19 | 03-Mar-19 | 04-Mar-19 | 05-Mar-19 | 06-Mar-19 | 07-Mar-19 | 08-Mar-19 | 09-Mar-19 | 10-Mar-19 | 11-Mar-19 | 12-Mar-19 | 13-Mar-19 | 14-Mar-19 | 15-Mar-19 | 16-Mar-19 | 17-Mar-19 | 18-Mar-19 | 19-Mar-19 | 20-Mar-19 | 21-Mar-19 | 22-Mar-19 | 23-Mar-19 | 24-Mar-19 | 25-Mar-19 | 26-Mar-19 | 27-Mar-19 | 28-Mar-19 | 29-Mar-19 | 30-Mar-19 | 31-Mar-19 | 01-Apr-19 | 02-Apr-19 | 03-Apr-19 | 04-Apr-19 | 05-Apr-19 | 06-Apr-19 | 07-Apr-19 | 08-Apr-19 | 09-Apr-19 | 10-Apr-19
A1010 | Mobilization and Site Office Installation | Cost-School | Cost-School | 990000 | 990000 | 96.67% | 957000 | Actual Units |  | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86 | 3417.86
A1010 | Mobilization and Site Office Installation | Cost-School | Cost-School | 990000 | 990000 | 96.67% | 957000 | Remaining Early Units | [281 empty] | 33000
A1010 | Mobilization and Site Office Installation | Cost-School | Cost-School | 990000 | 990000 | 96.67% | 957000 | Remaining Late Units | [281 empty] | 1990-05-07
A1010 | Mobilization and Site Office Installation | Man-Power | Man-Power | 96 | 0 | 96.67% | 9280% | Actual Units |  | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
A1010 | Mobilization and Site Office Installation | Man-Power | Man-Power | 96 | 0 | 96.67% | 9280% | Remaining Early Units | [281 empty] | 3.2
A1010 | Mobilization and Site Office Installation | Man-Power | Man-Power | 96 | 0 | 96.67% | 9280% | Remaining Late Units | [281 empty] | 3.2
3-MA1000 | Concrete | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [6 empty] | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57
3-MA1000 | Concrete | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1000 | Concrete | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
2-MS1030 | Doors and window | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [6 empty] | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
2-MS1030 | Doors and window | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1030 | Doors and window | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
2-MS1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Actual Units | [6 empty] | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29
2-MS1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Early Units
2-MS1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Late Units
2-MS1060 | Electrical | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [6 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1060 | Electrical | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1060 | Electrical | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
2-MS1070 | Plumbing | Man-Power | Man-Power | 23.04 | 0 | 50% | 1152% | Actual Units | [6 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
2-MS1070 | Plumbing | Man-Power | Man-Power | 23.04 | 0 | 50% | 1152% | Remaining Early Units | [281 empty] | 3.29 | 3.29 | 3.29 | 1.65
2-MS1070 | Plumbing | Man-Power | Man-Power | 23.04 | 0 | 50% | 1152% | Remaining Late Units | [342 empty] | 0.26 | 3.29 | 3.29 | 3.29 | 1.39
A1030 | Excavation Works | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Actual Units | [7 empty] | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680 | 53680
A1030 | Excavation Works | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Remaining Early Units
A1030 | Excavation Works | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Remaining Late Units
A1030 | Excavation Works | Man-Power | Man-Power | 250 | 0 | 100% | 25000% | Actual Units | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
A1030 | Excavation Works | Man-Power | Man-Power | 250 | 0 | 100% | 25000% | Remaining Early Units
A1030 | Excavation Works | Man-Power | Man-Power | 250 | 0 | 100% | 25000% | Remaining Late Units
2-MS1000 | Concrete | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [8 empty] | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | 0.58
2-MS1000 | Concrete | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1000 | Concrete | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
2-MS1010 | Block | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [8 empty] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05
2-MS1010 | Block | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1010 | Block | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
2-MS1020 | Ceramic | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [8 empty] | 23.04
2-MS1020 | Ceramic | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1020 | Ceramic | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
1-SUB-100 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [10 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-100 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-100 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
4-MD1000 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [15 empty] | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64
4-MD1000 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
4-MD1000 | Concrete | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
4-MD1030 | Doors and window | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Actual Units | [20 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
4-MD1030 | Doors and window | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Remaining Early Units
4-MD1030 | Doors and window | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Remaining Late Units
4-MD1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 90% | 9000% | Actual Units | [20 empty] | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34
4-MD1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 90% | 9000% | Remaining Early Units | [281 empty] | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67
4-MD1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 90% | 9000% | Remaining Late Units | [343 empty] | 1.17 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 0.5
4-MD1050 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 95% | 730% | Actual Units | [20 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
4-MD1050 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 95% | 730% | Remaining Early Units | [281 empty] | 0.13 | 0.13 | 0.13
4-MD1050 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 95% | 730% | Remaining Late Units | [349 empty] | 0.07 | 0.13 | 0.13 | 0.05
4-MD1060 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Actual Units | [20 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
4-MD1060 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Remaining Early Units | [281 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1060 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Remaining Late Units | [346 empty] | 0.07 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.05
4-MD1070 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Actual Units | [20 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
4-MD1070 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Remaining Early Units | [284 empty] | 0.06 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.06
4-MD1070 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 90% | 691% | Remaining Late Units | [346 empty] | 0.07 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.05
4-MD1100 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 80% | 614% | Actual Units | [20 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
4-MD1100 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 80% | 614% | Remaining Early Units | [288 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1100 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 80% | 614% | Remaining Late Units | [340 empty] | 0.07 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.05
4-MD1010 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [21 empty] | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
4-MD1010 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
4-MD1010 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
3-MA1010 | Block | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [22 empty] | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12
3-MA1010 | Block | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1010 | Block | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
3-MA1030 | Doors and window | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [22 empty] | 61.44
3-MA1030 | Doors and window | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1030 | Doors and window | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
3-MA1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Actual Units | [22 empty] | 100
3-MA1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Early Units
3-MA1040 | Wood Works | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Late Units
3-MA1050 | AC Machine | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [22 empty] | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04
3-MA1050 | AC Machine | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1050 | AC Machine | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
3-MA1070 | Plumbing | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [22 empty] | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95
3-MA1070 | Plumbing | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1070 | Plumbing | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
4-MD1020 | Ceramic | Man-Power | Man-Power | 50 | 0 | 80% | 4000% | Actual Units | [22 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
4-MD1020 | Ceramic | Man-Power | Man-Power | 50 | 0 | 80% | 4000% | Remaining Early Units | [281 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
4-MD1020 | Ceramic | Man-Power | Man-Power | 50 | 0 | 80% | 4000% | Remaining Late Units | [337 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
3-MA1020 | Ceramic | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [23 empty] | 61.44
3-MA1020 | Ceramic | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1020 | Ceramic | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
3-MA1060 | Electrical | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [23 empty] | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12
3-MA1060 | Electrical | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1060 | Electrical | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
3-MA1100 | Fire Fighting | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [23 empty] | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12 | 1.12
3-MA1100 | Fire Fighting | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
3-MA1100 | Fire Fighting | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
A1050 | Foundation Works | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Actual Units
A1050 | Foundation Works | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Early Units | [282 empty] | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56
A1050 | Foundation Works | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Late Units | [282 empty] | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56 | 59155.56
A1050 | Foundation Works | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Actual Units
A1050 | Foundation Works | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Early Units | [282 empty] | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22
A1050 | Foundation Works | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Late Units | [282 empty] | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22
1-SUB-110 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-110 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-110 | Block | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
1-SUB-150 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-150 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-150 | AC Machine | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
1-SUB-160 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-160 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-160 | Electrical | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
1-SUB-170 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-170 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-170 | Plumbing | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
1-SUB-200 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [50 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-200 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-200 | Fire Fighting | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
2-MS1050 | AC Machine | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Actual Units | [65 empty] | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84
2-MS1050 | AC Machine | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Early Units
2-MS1050 | AC Machine | Man-Power | Man-Power | 23.04 | 0 | 100% | 2304% | Remaining Late Units
1-SDS100 | Structural Drawings | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Actual Units | [69 empty] | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11
1-SDS100 | Structural Drawings | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Remaining Early Units
1-SDS100 | Structural Drawings | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Remaining Late Units
2-SDA1000 | Structural Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [74 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1000 | Structural Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
2-SDA1000 | Structural Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
1-SUB-120 | Ceramic | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [100 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-120 | Ceramic | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-120 | Ceramic | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
1-SUB-130 | Doors and window | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [100 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-130 | Doors and window | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-130 | Doors and window | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
A1210 | Ground Floor Slab | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Actual Units
A1210 | Ground Floor Slab | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Early Units | [327 empty] | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100
A1210 | Ground Floor Slab | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Late Units | [327 empty] | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100 | 133100
A1210 | Ground Floor Slab | Man-Power | Man-Power | 346 | 0 | 0% | 0% | Actual Units
A1210 | Ground Floor Slab | Man-Power | Man-Power | 346 | 0 | 0% | 0% | Remaining Early Units | [327 empty] | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3
A1210 | Ground Floor Slab | Man-Power | Man-Power | 346 | 0 | 0% | 0% | Remaining Late Units | [327 empty] | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 | 17.3
1-SDS110 | Finishes Drawings | Man-Power | Man-Power | 123 | 0 | 100% | 12300% | Actual Units | [107 empty] | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79 | 8.79
1-SDS110 | Finishes Drawings | Man-Power | Man-Power | 123 | 0 | 100% | 12300% | Remaining Early Units
1-SDS110 | Finishes Drawings | Man-Power | Man-Power | 123 | 0 | 100% | 12300% | Remaining Late Units
2-SDA1010 | Finishes Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Actual Units | [114 empty] | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39
2-SDA1010 | Finishes Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Early Units
2-SDA1010 | Finishes Drawings | Man-Power | Man-Power | 61.44 | 0 | 100% | 6144% | Remaining Late Units
1-SUB-140 | Wood Works | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Actual Units | [120 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-140 | Wood Works | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Early Units
1-SUB-140 | Wood Works | Man-Power | Man-Power | 7.68 | 0 | 100% | 768% | Remaining Late Units
A1220 | Ground Floor Columns | Cost-School | Cost-School | 2662000 | 2662000 | 100% | 266200000% | Actual Units | [131 empty] | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67 | 177466.67
A1220 | Ground Floor Columns | Cost-School | Cost-School | 2662000 | 2662000 | 100% | 266200000% | Remaining Early Units
A1220 | Ground Floor Columns | Cost-School | Cost-School | 2662000 | 2662000 | 100% | 266200000% | Remaining Late Units
A1220 | Ground Floor Columns | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Actual Units | [131 empty] | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33
A1220 | Ground Floor Columns | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Remaining Early Units
A1220 | Ground Floor Columns | Man-Power | Man-Power | 20 | 0 | 100% | 2000% | Remaining Late Units
1-SDS120 | Mechanical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Actual Units | [134 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11
1-SDS120 | Mechanical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Early Units | [281 empty] | 1.43 | 1.43 | 1.14
1-SDS120 | Mechanical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Late Units | [346 empty] | 0.26 | 1.43 | 1.43 | 0.89
1-SDS130 | Electrical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Actual Units | [134 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11
1-SDS130 | Electrical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Early Units | [281 empty] | 1.43 | 1.43 | 1.14
1-SDS130 | Electrical Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Late Units | [342 empty] | 0.54 | 1.43 | 1.43 | 0.6
1-SDS150 | Plumbing Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Actual Units | [134 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11
1-SDS150 | Plumbing Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Early Units | [281 empty] | 1.43 | 1.43 | 1.14
1-SDS150 | Plumbing Drawings | Man-Power | Man-Power | 20 | 0 | 80% | 1600% | Remaining Late Units | [341 empty] | 1.11 | 1.43 | 1.43 | 0.03
2-SDA1020 | Mechanical Drawings | Man-Power | Man-Power | 61.44 | 0 | 80% | 4915% | Actual Units | [134 empty] | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
2-SDA1020 | Mechanical Drawings | Man-Power | Man-Power | 61.44 | 0 | 80% | 4915% | Remaining Early Units | [283 empty] | 0.88 | 4.39 | 4.39 | 2.63
2-SDA1020 | Mechanical Drawings | Man-Power | Man-Power | 61.44 | 0 | 80% | 4915% | Remaining Late Units | [349 empty] | 1.66 | 4.39 | 4.39 | 1.85
2-SDA1030 | Electrical Drawings | Man-Power | Man-Power | 61.44 | 0 | 50% | 3072% | Actual Units | [134 empty] | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21
2-SDA1030 | Electrical Drawings | Man-Power | Man-Power | 61.44 | 0 | 50% | 3072% | Remaining Early Units | [283 empty] | 0.88 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 3.51
2-SDA1030 | Electrical Drawings | Man-Power | Man-Power | 61.44 | 0 | 50% | 3072% | Remaining Late Units | [345 empty] | 2.54 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 1.85
2-SDA1040 | Fire Fighting Drawings | Man-Power | Man-Power | 15.36 | 0 | 50% | 768% | Actual Units | [134 empty] | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
2-SDA1040 | Fire Fighting Drawings | Man-Power | Man-Power | 15.36 | 0 | 50% | 768% | Remaining Early Units | [292 empty] | 0.88 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.22
2-SDA1040 | Fire Fighting Drawings | Man-Power | Man-Power | 15.36 | 0 | 50% | 768% | Remaining Late Units | [345 empty] | 0.64 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.46
2-SDA1050 | Plumbing Drawings | Man-Power | Man-Power | 61.44 | 0 | 40% | 2458% | Actual Units | [134 empty] | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17
2-SDA1050 | Plumbing Drawings | Man-Power | Man-Power | 61.44 | 0 | 40% | 2458% | Remaining Early Units | [283 empty] | 0.88 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 0.88
2-SDA1050 | Plumbing Drawings | Man-Power | Man-Power | 61.44 | 0 | 40% | 2458% | Remaining Late Units | [344 empty] | 4.3 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 4.39 | 1.85
1-SDS140 | Fire Fighting Drawings | Man-Power | Man-Power | 20 | 0 | 20% | 400% | Actual Units | [141 empty] | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
1-SDS140 | Fire Fighting Drawings | Man-Power | Man-Power | 20 | 0 | 20% | 400% | Remaining Early Units | [281 empty] | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 0.29
1-SDS140 | Fire Fighting Drawings | Man-Power | Man-Power | 20 | 0 | 20% | 400% | Remaining Late Units | [334 empty] | 1.11 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | 0.6
A1230 | Roof Slab | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Actual Units | [145 empty] | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67 | 89466.67
A1230 | Roof Slab | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Remaining Early Units
A1230 | Roof Slab | Cost-School | Cost-School | 1342000 | 1342000 | 100% | 134200000% | Remaining Late Units
A1230 | Roof Slab | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Actual Units | [145 empty] | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33
A1230 | Roof Slab | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Remaining Early Units
A1230 | Roof Slab | Man-Power | Man-Power | 50 | 0 | 100% | 5000% | Remaining Late Units
A1250 | Block Works | Cost-School | Cost-School | 2186800 | 2186800 | 100% | 218680000% | Actual Units | [159 empty] | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340 | 109340
A1250 | Block Works | Cost-School | Cost-School | 2186800 | 2186800 | 100% | 218680000% | Remaining Early Units
A1250 | Block Works | Cost-School | Cost-School | 2186800 | 2186800 | 100% | 218680000% | Remaining Late Units
A1250 | Block Works | Man-Power | Man-Power | 200 | 0 | 100% | 20000% | Actual Units | [159 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
A1250 | Block Works | Man-Power | Man-Power | 200 | 0 | 100% | 20000% | Remaining Early Units
A1250 | Block Works | Man-Power | Man-Power | 200 | 0 | 100% | 20000% | Remaining Late Units
A1270 | Ceramic | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Actual Units | [183 empty] | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000
A1270 | Ceramic | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Remaining Early Units
A1270 | Ceramic | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Remaining Late Units
A1270 | Ceramic | Man-Power | Man-Power | 412.8 | 0 | 100% | 41280% | Actual Units | [183 empty] | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4
A1270 | Ceramic | Man-Power | Man-Power | 412.8 | 0 | 100% | 41280% | Remaining Early Units
A1270 | Ceramic | Man-Power | Man-Power | 412.8 | 0 | 100% | 41280% | Remaining Late Units
A1410 | Roof Waterproofing woks | Cost-School | Cost-School | 2200 | 2200 | 100% | 220000% | Actual Units | [184 empty] | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11 | 61.11
A1410 | Roof Waterproofing woks | Cost-School | Cost-School | 2200 | 2200 | 100% | 220000% | Remaining Early Units
A1410 | Roof Waterproofing woks | Cost-School | Cost-School | 2200 | 2200 | 100% | 220000% | Remaining Late Units
A1410 | Roof Waterproofing woks | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Actual Units | [184 empty] | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78
A1410 | Roof Waterproofing woks | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Early Units
A1410 | Roof Waterproofing woks | Man-Power | Man-Power | 100 | 0 | 100% | 10000% | Remaining Late Units
A1260 | Plaster | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Actual Units | [189 empty] | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000 | 176000
A1260 | Plaster | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Remaining Early Units
A1260 | Plaster | Cost-School | Cost-School | 2640000 | 2640000 | 100% | 264000000% | Remaining Late Units
A1260 | Plaster | Man-Power | Man-Power | 312 | 0 | 100% | 31200% | Actual Units | [189 empty] | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | 20.8
A1260 | Plaster | Man-Power | Man-Power | 312 | 0 | 100% | 31200% | Remaining Early Units
A1260 | Plaster | Man-Power | Man-Power | 312 | 0 | 100% | 31200% | Remaining Late Units
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Cost-School | Cost-School | 1669800 | 1669800 | 80% | 133584000% | Actual Units | [215 empty] | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240 | 20240
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Cost-School | Cost-School | 1669800 | 1669800 | 80% | 133584000% | Remaining Early Units | [347 empty] | 166980 | 166980
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Cost-School | Cost-School | 1669800 | 1669800 | 80% | 133584000% | Remaining Late Units | [347 empty] | 166980 | 166980
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Man-Power | Man-Power | 450 | 0 | 80% | 36000% | Actual Units | [215 empty] | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45 | 5.45
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Man-Power | Man-Power | 450 | 0 | 80% | 36000% | Remaining Early Units | [347 empty] | 45 | 45
A1170 | MEP 1St FIX (Conduits, pipes inside walls) | Man-Power | Man-Power | 450 | 0 | 80% | 36000% | Remaining Late Units | [347 empty] | 45 | 45
1-SUB-190 | Landscaping | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Actual Units
1-SUB-190 | Landscaping | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Remaining Early Units | [281 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-190 | Landscaping | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Remaining Late Units | [323 empty] | 0.64 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.46
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Cost-School | Cost-School | 4569400 | 4569400 | 80% | 365552000% | Actual Units | [225 empty] | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14 | 65277.14
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Cost-School | Cost-School | 4569400 | 4569400 | 80% | 365552000% | Remaining Early Units | [349 empty] | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Cost-School | Cost-School | 4569400 | 4569400 | 80% | 365552000% | Remaining Late Units | [352 empty] | 88214.81 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 152313.33 | 64098.53
A1280 | Ceiling Works | Cost-School | Cost-School | 2860000 | 2860000 | 100% | 286000000% | Actual Units | [225 empty] | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33 | 95333.33
A1280 | Ceiling Works | Cost-School | Cost-School | 2860000 | 2860000 | 100% | 286000000% | Remaining Early Units
A1280 | Ceiling Works | Cost-School | Cost-School | 2860000 | 2860000 | 100% | 286000000% | Remaining Late Units
A1300 | Doors and windows Works | Cost-School | Cost-School | 3960000 | 3960000 | 100% | 396000000% | Actual Units | [225 empty] | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18 | 232941.18
A1300 | Doors and windows Works | Cost-School | Cost-School | 3960000 | 3960000 | 100% | 396000000% | Remaining Early Units
A1300 | Doors and windows Works | Cost-School | Cost-School | 3960000 | 3960000 | 100% | 396000000% | Remaining Late Units
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Man-Power | Man-Power | 964 | 0 | 80% | 77120% | Actual Units | [225 empty] | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77 | 13.77
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Man-Power | Man-Power | 964 | 0 | 80% | 77120% | Remaining Early Units | [349 empty] | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13
A1180 | MEP 2nd Fix (above ceiling AC and Electrical Works) | Man-Power | Man-Power | 964 | 0 | 80% | 77120% | Remaining Late Units | [352 empty] | 18.61 | 32.13 | 32.13 | 32.13 | 32.13 | 32.13 | 13.52
A1280 | Ceiling Works | Man-Power | Man-Power | 314 | 0 | 100% | 31400% | Actual Units | [225 empty] | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47 | 10.47
A1280 | Ceiling Works | Man-Power | Man-Power | 314 | 0 | 100% | 31400% | Remaining Early Units
A1280 | Ceiling Works | Man-Power | Man-Power | 314 | 0 | 100% | 31400% | Remaining Late Units
A1300 | Doors and windows Works | Man-Power | Man-Power | 201.6 | 0 | 100% | 20160% | Actual Units | [225 empty] | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86 | 11.86
A1300 | Doors and windows Works | Man-Power | Man-Power | 201.6 | 0 | 100% | 20160% | Remaining Early Units
A1300 | Doors and windows Works | Man-Power | Man-Power | 201.6 | 0 | 100% | 20160% | Remaining Late Units
A1310 | Plaster | Cost-School | Cost-School | 22000 | 22000 | 100% | 2200000% | Actual Units | [227 empty] | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200
A1310 | Plaster | Cost-School | Cost-School | 22000 | 22000 | 100% | 2200000% | Remaining Early Units
A1310 | Plaster | Cost-School | Cost-School | 22000 | 22000 | 100% | 2200000% | Remaining Late Units
A1310 | Plaster | Man-Power | Man-Power | 115.2 | 0 | 100% | 11520% | Actual Units | [227 empty] | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52 | 11.52
A1310 | Plaster | Man-Power | Man-Power | 115.2 | 0 | 100% | 11520% | Remaining Early Units
A1310 | Plaster | Man-Power | Man-Power | 115.2 | 0 | 100% | 11520% | Remaining Late Units
A1340 | Epoxy Coating-Services Area | Cost-School | Cost-School | 3960000 | 3960000 | 99% | 392040000% | Actual Units | [242 empty] | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08 | 100523.08
A1340 | Epoxy Coating-Services Area | Cost-School | Cost-School | 3960000 | 3960000 | 99% | 392040000% | Remaining Early Units | [349 empty] | 39600
A1340 | Epoxy Coating-Services Area | Cost-School | Cost-School | 3960000 | 3960000 | 99% | 392040000% | Remaining Late Units | [349 empty] | 39600
A1340 | Epoxy Coating-Services Area | Man-Power | Man-Power | 120 | 0 | 99% | 11880% | Actual Units | [242 empty] | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05 | 3.05
A1340 | Epoxy Coating-Services Area | Man-Power | Man-Power | 120 | 0 | 99% | 11880% | Remaining Early Units | [349 empty] | 1.2
A1340 | Epoxy Coating-Services Area | Man-Power | Man-Power | 120 | 0 | 99% | 11880% | Remaining Late Units | [349 empty] | 1.2
A1290 | Painting - 1st Coat | Cost-School | Cost-School | 6820000 | 6820000 | 100% | 682000000% | Actual Units | [261 empty] | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000 | 682000
A1290 | Painting - 1st Coat | Cost-School | Cost-School | 6820000 | 6820000 | 100% | 682000000% | Remaining Early Units
A1290 | Painting - 1st Coat | Cost-School | Cost-School | 6820000 | 6820000 | 100% | 682000000% | Remaining Late Units
A1290 | Painting - 1st Coat | Man-Power | Man-Power | 488 | 0 | 100% | 48800% | Actual Units | [261 empty] | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8 | 48.8
A1290 | Painting - 1st Coat | Man-Power | Man-Power | 488 | 0 | 100% | 48800% | Remaining Early Units
A1290 | Painting - 1st Coat | Man-Power | Man-Power | 488 | 0 | 100% | 48800% | Remaining Late Units
A1350 | Kitchen Cabinets | Cost-School | Cost-School | 3740000 | 3740000 | 98.99% | 370234028% | Actual Units | [272 empty] | 411371.14 | 411371.14 | 411371.14 | 411371.14 | 411371.14 | 411371.14 | 411371.14 | 411371.14 | 411371.14
A1350 | Kitchen Cabinets | Cost-School | Cost-School | 3740000 | 3740000 | 98.99% | 370234028% | Remaining Early Units | [349 empty] | 37659.72
A1350 | Kitchen Cabinets | Cost-School | Cost-School | 3740000 | 3740000 | 98.99% | 370234028% | Remaining Late Units | [349 empty] | 37659.72
A1350 | Kitchen Cabinets | Man-Power | Man-Power | 316 | 0 | 98.99% | 31282% | Actual Units | [272 empty] | 34.76 | 34.76 | 34.76 | 34.76 | 34.76 | 34.76 | 34.76 | 34.76 | 34.76
A1350 | Kitchen Cabinets | Man-Power | Man-Power | 316 | 0 | 98.99% | 31282% | Remaining Early Units | [349 empty] | 3.18
A1350 | Kitchen Cabinets | Man-Power | Man-Power | 316 | 0 | 98.99% | 31282% | Remaining Late Units | [349 empty] | 3.18
E1070 | Fence Works | Cost-School | Cost-School | 4840000 | 4840000 | 80% | 387200000% | Actual Units | [280 empty] | 3872000
E1070 | Fence Works | Cost-School | Cost-School | 4840000 | 4840000 | 80% | 387200000% | Remaining Early Units | [374 empty] | 56063.33 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 40736.67
E1070 | Fence Works | Cost-School | Cost-School | 4840000 | 4840000 | 80% | 387200000% | Remaining Late Units | [374 empty] | 56063.33 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 96800 | 40736.67
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Cost-School | Cost-School | 5618800 | 5618800 | 60% | 337128000% | Actual Units | [280 empty] | 3371280
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Cost-School | Cost-School | 5618800 | 5618800 | 60% | 337128000% | Remaining Early Units | [358 empty] | 81355.54 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 59114.46
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Cost-School | Cost-School | 5618800 | 5618800 | 60% | 337128000% | Remaining Late Units | [358 empty] | 81355.54 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 140470 | 59114.46
E1070 | Fence Works | Man-Power | Man-Power | 600 | 0 | 80% | 48000% | Actual Units | [280 empty] | 480
E1070 | Fence Works | Man-Power | Man-Power | 600 | 0 | 80% | 48000% | Remaining Early Units | [374 empty] | 6.95 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 5.05
E1070 | Fence Works | Man-Power | Man-Power | 600 | 0 | 80% | 48000% | Remaining Late Units | [374 empty] | 6.95 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 5.05
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Man-Power | Man-Power | 800 | 0 | 60% | 48000% | Actual Units | [280 empty] | 480
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Man-Power | Man-Power | 800 | 0 | 60% | 48000% | Remaining Early Units | [358 empty] | 11.58 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8.42
A1190 | MEP Final Fix (Light fixtures ,fire alarm ,AC diffusers ) | Man-Power | Man-Power | 800 | 0 | 60% | 48000% | Remaining Late Units | [358 empty] | 11.58 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8.42
E1071 | External Tiling Works | Cost-School | Cost-School | 880000 | 880000 | 50% | 44000000% | Actual Units | [281 empty] | 440000
E1071 | External Tiling Works | Cost-School | Cost-School | 880000 | 880000 | 50% | 44000000% | Remaining Early Units | [384 empty] | 20386.67 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 32413.33
E1071 | External Tiling Works | Cost-School | Cost-School | 880000 | 880000 | 50% | 44000000% | Remaining Late Units | [431 empty] | 2786.67 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 35200 | 14813.33
E1071 | External Tiling Works | Man-Power | Man-Power | 250 | 0 | 50% | 12500% | Actual Units | [281 empty] | 125
E1071 | External Tiling Works | Man-Power | Man-Power | 250 | 0 | 50% | 12500% | Remaining Early Units | [384 empty] | 5.79 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9.21
E1071 | External Tiling Works | Man-Power | Man-Power | 250 | 0 | 50% | 12500% | Remaining Late Units | [431 empty] | 0.79 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4.21
A1240 | Parapet | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Actual Units
A1240 | Parapet | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Early Units | [347 empty] | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33
A1240 | Parapet | Cost-School | Cost-School | 2662000 | 2662000 | 0% | 0% | Remaining Late Units | [347 empty] | 128478.47 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 221833.33 | 93354.86
A1320 | Painting | Cost-School | Cost-School | 3080 | 3080 | 0% | 0% | Actual Units
A1320 | Painting | Cost-School | Cost-School | 3080 | 3080 | 0% | 0% | Remaining Early Units | [359 empty] | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33
A1320 | Painting | Cost-School | Cost-School | 3080 | 3080 | 0% | 0% | Remaining Late Units | [359 empty] | 118.92 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 205.33 | 86.41
E1081 | Green Area Works | Cost-School | Cost-School | 0 | 0 | 0% | 0% | Actual Units
E1081 | Green Area Works | Cost-School | Cost-School | 0 | 0 | 0% | 0% | Remaining Early Units
E1081 | Green Area Works | Cost-School | Cost-School | 0 | 0 | 0% | 0% | Remaining Late Units
A1080 | Project Handing Over and Authority approvals | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Actual Units
A1080 | Project Handing Over and Authority approvals | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Early Units | [444 empty] | 1.45 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.05
A1080 | Project Handing Over and Authority approvals | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Late Units | [444 empty] | 1.45 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.05
A1240 | Parapet | Man-Power | Man-Power | 184 | 0 | 0% | 0% | Actual Units
A1240 | Parapet | Man-Power | Man-Power | 184 | 0 | 0% | 0% | Remaining Early Units | [347 empty] | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33
A1240 | Parapet | Man-Power | Man-Power | 184 | 0 | 0% | 0% | Remaining Late Units | [347 empty] | 8.88 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 15.33 | 6.45
A1320 | Painting | Man-Power | Man-Power | 96 | 0 | 0% | 0% | Actual Units
A1320 | Painting | Man-Power | Man-Power | 96 | 0 | 0% | 0% | Remaining Early Units | [359 empty] | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4
A1320 | Painting | Man-Power | Man-Power | 96 | 0 | 0% | 0% | Remaining Late Units | [359 empty] | 3.71 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 2.69
E1081 | Green Area Works | Man-Power | Man-Power | 46 | 0 | 0% | 0% | Actual Units
E1081 | Green Area Works | Man-Power | Man-Power | 46 | 0 | 0% | 0% | Remaining Early Units | [392 empty] | 0.67 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 0.48
E1081 | Green Area Works | Man-Power | Man-Power | 46 | 0 | 0% | 0% | Remaining Late Units | [404 empty] | 0.67 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 0.48
E1080 | Installation of Wheel Stopper & Corner Gaurd | Cost-School | Cost-School | 2420000 | 2420000 | 0% | 0% | Actual Units
E1080 | Installation of Wheel Stopper & Corner Gaurd | Cost-School | Cost-School | 2420000 | 2420000 | 0% | 0% | Remaining Early Units | [384 empty] | 23359.72 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 16973.61
E1080 | Installation of Wheel Stopper & Corner Gaurd | Cost-School | Cost-School | 2420000 | 2420000 | 0% | 0% | Remaining Late Units | [384 empty] | 23359.72 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 40333.33 | 16973.61
A1360 | Vanity Counter | Cost-School | Cost-School | 2860000 | 2860000 | 0% | 0% | Actual Units
A1360 | Vanity Counter | Cost-School | Cost-School | 2860000 | 2860000 | 0% | 0% | Remaining Early Units | [349 empty] | 414104.17 | 715000 | 715000 | 715000 | 300895.83
A1360 | Vanity Counter | Cost-School | Cost-School | 2860000 | 2860000 | 0% | 0% | Remaining Late Units | [349 empty] | 414104.17 | 715000 | 715000 | 715000 | 300895.83
A1370 | Wooden Doors | Cost-School | Cost-School | 1540000 | 1540000 | 0% | 0% | Actual Units
A1370 | Wooden Doors | Cost-School | Cost-School | 1540000 | 1540000 | 0% | 0% | Remaining Early Units | [353 empty] | 178383.33 | 308000 | 308000 | 308000 | 308000 | 129616.67
A1370 | Wooden Doors | Cost-School | Cost-School | 1540000 | 1540000 | 0% | 0% | Remaining Late Units | [353 empty] | 178383.33 | 308000 | 308000 | 308000 | 308000 | 129616.67
A1380 | Wardrobes | Cost-School | Cost-School | 6160000 | 6160000 | 0% | 0% | Actual Units
A1380 | Wardrobes | Cost-School | Cost-School | 6160000 | 6160000 | 0% | 0% | Remaining Early Units | [368 empty] | 71353.33 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 51846.67
A1380 | Wardrobes | Cost-School | Cost-School | 6160000 | 6160000 | 0% | 0% | Remaining Late Units | [371 empty] | 71353.33 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 123200 | 51846.67
A1390 | Mirrors & Bath Accessories | Cost-School | Cost-School | 880000 | 880000 | 0% | 0% | Actual Units
A1390 | Mirrors & Bath Accessories | Cost-School | Cost-School | 880000 | 880000 | 0% | 0% | Remaining Early Units | [421 empty] | 25483.33 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 18516.67
A1390 | Mirrors & Bath Accessories | Cost-School | Cost-School | 880000 | 880000 | 0% | 0% | Remaining Late Units | [424 empty] | 25483.33 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 44000 | 18516.67
A1330 | Painting Final Coat | Cost-School | Cost-School | 440000 | 440000 | 0% | 0% | Actual Units
A1330 | Painting Final Coat | Cost-School | Cost-School | 440000 | 440000 | 0% | 0% | Remaining Early Units | [413 empty] | 31854.17 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 23145.83
A1330 | Painting Final Coat | Cost-School | Cost-School | 440000 | 440000 | 0% | 0% | Remaining Late Units | [416 empty] | 31854.17 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 23145.83
A1400 | Balcony Handrails | Cost-School | Cost-School | 1320 | 1320 | 0% | 0% | Actual Units
A1400 | Balcony Handrails | Cost-School | Cost-School | 1320 | 1320 | 0% | 0% | Remaining Early Units | [359 empty] | 264 | 264 | 264 | 264 | 264
A1400 | Balcony Handrails | Cost-School | Cost-School | 1320 | 1320 | 0% | 0% | Remaining Late Units | [439 empty] | 152.9 | 264 | 264 | 264 | 264 | 111.1
1-SUB-180 | Mirrors & Bath Accessories | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Actual Units
1-SUB-180 | Mirrors & Bath Accessories | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Remaining Early Units | [281 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1-SUB-180 | Mirrors & Bath Accessories | Man-Power | Man-Power | 7.68 | 0 | 0% | 0% | Remaining Late Units | [343 empty] | 0.64 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.46
2-MS1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 11.52 | 0 | 0% | 0% | Actual Units
2-MS1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 11.52 | 0 | 0% | 0% | Remaining Early Units | [288 empty] | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65
2-MS1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 11.52 | 0 | 0% | 0% | Remaining Late Units | [350 empty] | 0.95 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 0.69
2-MS1090 | Landscaping | Man-Power | Man-Power | 150 | 0 | 0% | 0% | Actual Units
2-MS1090 | Landscaping | Man-Power | Man-Power | 150 | 0 | 0% | 0% | Remaining Early Units | [288 empty] | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43
2-MS1090 | Landscaping | Man-Power | Man-Power | 150 | 0 | 0% | 0% | Remaining Late Units | [330 empty] | 12.41 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 21.43 | 9.02
2-MS1100 | Fire Fighting | Man-Power | Man-Power | 23.04 | 0 | 0% | 0% | Actual Units
2-MS1100 | Fire Fighting | Man-Power | Man-Power | 23.04 | 0 | 0% | 0% | Remaining Early Units | [281 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29
2-MS1100 | Fire Fighting | Man-Power | Man-Power | 23.04 | 0 | 0% | 0% | Remaining Late Units | [333 empty] | 1.91 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 1.39
3-MA1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 61.44 | 0 | 0% | 0% | Actual Units
3-MA1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 61.44 | 0 | 0% | 0% | Remaining Early Units | [295 empty] | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78
3-MA1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 61.44 | 0 | 0% | 0% | Remaining Late Units | [357 empty] | 5.08 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 3.69
3-MA1090 | Landscaping | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Actual Units
3-MA1090 | Landscaping | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Early Units | [295 empty] | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29
3-MA1090 | Landscaping | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Late Units | [337 empty] | 8.27 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 14.29 | 6.01
4-MD1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 8 | 0 | 0% | 0% | Actual Units
4-MD1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 8 | 0 | 0% | 0% | Remaining Early Units | [302 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
4-MD1080 | Mirrors & Bath Accessories | Man-Power | Man-Power | 8 | 0 | 0% | 0% | Remaining Late Units | [364 empty] | 0.08 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.06
4-MD1090 | Landscaping | Man-Power | Man-Power | 200 | 0 | 0% | 0% | Actual Units
4-MD1090 | Landscaping | Man-Power | Man-Power | 200 | 0 | 0% | 0% | Remaining Early Units | [302 empty] | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33
4-MD1090 | Landscaping | Man-Power | Man-Power | 200 | 0 | 0% | 0% | Remaining Late Units | [344 empty] | 1.93 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 1.4
E1080 | Installation of Wheel Stopper & Corner Gaurd | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Actual Units
E1080 | Installation of Wheel Stopper & Corner Gaurd | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Early Units | [384 empty] | 0.97 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 0.7
E1080 | Installation of Wheel Stopper & Corner Gaurd | Man-Power | Man-Power | 100 | 0 | 0% | 0% | Remaining Late Units | [384 empty] | 0.97 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 1.67 | 0.7
A1400 | Balcony Handrails | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Actual Units
A1400 | Balcony Handrails | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Remaining Early Units | [359 empty] | 4.8 | 4.8 | 4.8 | 4.8 | 4.8
A1400 | Balcony Handrails | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Remaining Late Units | [439 empty] | 2.78 | 4.8 | 4.8 | 4.8 | 4.8 | 2.02
A1390 | Mirrors & Bath Accessories | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Actual Units
A1390 | Mirrors & Bath Accessories | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Early Units | [421 empty] | 1.45 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.05
A1390 | Mirrors & Bath Accessories | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Late Units | [424 empty] | 1.45 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.05
A1330 | Painting Final Coat | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Actual Units
A1330 | Painting Final Coat | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Early Units | [413 empty] | 3.62 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 2.63
A1330 | Painting Final Coat | Man-Power | Man-Power | 50 | 0 | 0% | 0% | Remaining Late Units | [416 empty] | 3.62 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 2.63
A1380 | Wardrobes | Man-Power | Man-Power | 688 | 0 | 0% | 0% | Actual Units
A1380 | Wardrobes | Man-Power | Man-Power | 688 | 0 | 0% | 0% | Remaining Early Units | [368 empty] | 7.97 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 5.79
A1380 | Wardrobes | Man-Power | Man-Power | 688 | 0 | 0% | 0% | Remaining Late Units | [371 empty] | 7.97 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 13.76 | 5.79
A1370 | Wooden Doors | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Actual Units
A1370 | Wooden Doors | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Remaining Early Units | [353 empty] | 34.75 | 60 | 60 | 60 | 60 | 25.25
A1370 | Wooden Doors | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Remaining Late Units | [353 empty] | 34.75 | 60 | 60 | 60 | 60 | 25.25
A1360 | Vanity Counter | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Actual Units
A1360 | Vanity Counter | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Remaining Early Units | [349 empty] | 43.44 | 75 | 75 | 75 | 31.56
A1360 | Vanity Counter | Man-Power | Man-Power | 300 | 0 | 0% | 0% | Remaining Late Units | [349 empty] | 43.44 | 75 | 75 | 75 | 31.56
HOV110 | Submission of As Built Drawings | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Actual Units
HOV110 | Submission of As Built Drawings | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Remaining Early Units | [374 empty] | 1.39 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 1.01
HOV110 | Submission of As Built Drawings | Man-Power | Man-Power | 24 | 0 | 0% | 0% | Remaining Late Units | [434 empty] | 1.39 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 1.01
HOV110 | Submission of As Built Drawings | Cost-School | Cost-School | 22000 | 22000 | 0% | 0% | Actual Units
HOV110 | Submission of As Built Drawings | Cost-School | Cost-School | 22000 | 22000 | 0% | 0% | Remaining Early Units | [374 empty] | 1274.17 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 925.83
HOV110 | Submission of As Built Drawings | Cost-School | Cost-School | 22000 | 22000 | 0% | 0% | Remaining Late Units | [434 empty] | 1274.17 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 925.83
A1080 | Project Handing Over and Authority approvals | Cost-School | Cost-School | 8800 | 8800 | 0% | 0% | Actual Units
A1080 | Project Handing Over and Authority approvals | Cost-School | Cost-School | 8800 | 8800 | 0% | 0% | Remaining Early Units | [444 empty] | 254.83 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 185.17
A1080 | Project Handing Over and Authority approvals | Cost-School | Cost-School | 8800 | 8800 | 0% | 0% | Remaining Late Units | [444 empty] | 254.83 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 185.17

## Info
Data Date
2018-10-09