## L01
L01 | L01-Description
L01-01 | Construction of Schools Program (Phase 9)

## L02
L02 | L02-Description
(New) | KEY DATES AND MILESTONES
(New)-1 | PRELIMINARIES
(New)-2 | PROCUREMENT
(New)-3 | ENGINEERING
(New)-4 | CONSTRUCTION
(New)-5 | HANDING OVER

## L03
L03 | L03-Description
(New) | KEY DATES AND MILESTONES
(New)-1 | PRELIMINARIES
(New)-2 | SUBCONTRACTOERS/SUPPLIERS
(New)-3 | MATERIAL SUBMISSION
(New)-4 | MATERIAL APPROVAL
(New)-5 | MATERIAL DEVIVERY
(New)-6 | SHOPDAWINGS SUBMITTAL
(New)-7 | SHOPDAWINGS APPROVAL
(New)-8 | VILLA BUILDING WORKS
(New)-9 | EXTERNAL WORKS
(New)-10 | HANDING OVER

## L04
L04 | L04-Description
(New) | KEY DATES AND MILESTONES
(New)-1 | PRELIMINARIES
(New)-2 | SUBCONTRACTOERS/SUPPLIERS
(New)-3 | MATERIAL SUBMISSION
(New)-4 | MATERIAL APPROVAL
(New)-5 | MATERIAL DEVIVERY
(New)-6 | SHOPDAWINGS SUBMITTAL
(New)-7 | SHOPDAWINGS APPROVAL
(New)-8 | SUB-STRUCTRE
(New)-9 | GROUND FLOOR
(New)-10 | ROOF
(New)-11 | GROUND FLOOR
(New)-12 | ROOF
(New)-13 | SERVICES
(New)-14 | EXTERNAL WORKS
(New)-15 | HANDING OVER